## EXE Dashboard
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5 |  |  |  | BOQ Version : | 6.13 | Effective Date: | 2023-02-08
[14 empty] | Domain: | CEO/CFO/CCO/NTM
| Description |  |  |  | Project Cost |  | As Build - Services | Contractor Allocated |  | As Build - Services Cost
| SD Project ID | 77G0056723 |  |  | Services Cost | 6223.96 | Civil | INTERNAL OR CONTRACTOR NAME |  | 0 |  |  |  | Department: | TECHNICAL
| SD Circuit ID | 77G0056723 |  |  | Free Issue Materials | 1321.495 | Jetting | INTERNAL OR CONTRACTOR NAME |  | 0
| Customer Name | VODACOM |  |  | Total BOQ Value | 7545.455 | Drilling | INTERNAL OR CONTRACTOR NAME |  | 0 |  |  |  | Document Type: | BILL OF QUANTITIES INFRASTRUCTURE BUILD
| Product | LINK BUSINESS |  |  |  |  | Re-instatement | INTERNAL OR CONTRACTOR NAME |  | 0
| Network Type | Blank |  |  |  |  | Floating | INTERNAL OR CONTRACTOR NAME |  | 0 |  |  |  | Document Name: | LA-TEC-BOQ-001
| Network Description | Blank |  |  | Cost/M |  | Focus | INTERNAL OR CONTRACTOR NAME |  | 0
| SD Date | 18/07/2023 |  |  | Physical Build Dist | 59 | Splicing | INTERNAL OR CONTRACTOR NAME |  | 0 |  |  |  | Revision Number: | 6.13
| OSP Planner | LUCAS |  |  | Cost/M Services Only | 105.5 |  | Services - Total AB BOQ Value |  | 0
| ISP Planner | LUCAS |  |  | Total Route Distance | 59 | [7 empty] | Effective Date: | 2023-02-08
| Surveyor 1 | VICTOR |  |  | Cost/M Total Project | 127.89
| Surveyor 2 | [12 empty] | Date of Next Revision: | 2023-05-01
| Survey Date | 2023-08-16 |  |  | Payback Period
| Link Description (Site A-Site B) | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton |  |  | MRC | 1500 | Variation Orders | VO - Service Cost | VO - % | VO - Material Cost | VO - % | VO - Total Cost | VO - %
| ISP SITE ID | G1VDA066 |  |  | Yearly MRC | 18000 | VO 1 | 0 | 0% | 0 | 0% | 0 | 0%
| Affected Region/s | WITKOPPEN RD |  |  | Special Build NRC | 0 | VO 2 | 0 | 0% | 0 | 0% | 0 | 0%
| Planning Date | 2023-08-22 |  |  | Payback Period in Years | 0.5 | VO 3 | 0 | 0% | 0 | 0% | 0 | 0%
| Senior Planner | NONOKO |  |  | Payback Period in Months | 6 | VO 4 | 0 | 0% | 0 | 0% | 0 | 0%
| Planning Manager | NONOKO
| Build Project Leader |  |  |  | Modal Split |  | Contractor | Service Cost |  | % Split
| Build Project Manager |  |  |  | Focus | 0% | Internal | 0 |  | #DIV/0!
[5 empty] | Existing Duct | 0% | External | 0 |  | #DIV/0!
[5 empty] | Civil | 100%
FTTH Only
[5 empty] | Total Number of Homes | 0
[5 empty] | Cost/Home(Services Only) | #DIV/0!
[5 empty] | Cost/Home(Total Project) | #DIV/0!
| WP 1 | Opt1 | WP 1 | Opt2 | WP 2 |  | OSP Instructions and Risks
| Sewer | 0 | Sewer | 0 | Sewer | 0
| Stormwater | 0 | Stormwater | 0 | Stormwater | 0
| Total Focus | 0 | Total Focus | 0 | Total Focus | 0
| LA Duct | 0 | LA Duct | 0 | LA Duct | 0
| Splicing on Existing Cable | 0 | Splicing on Existing Cable | 0 | Splicing on Existing Cable | 0
| Total Existing | 0 | Total Existing | 0 | Total Existing | 0
| 3rd Party Duct | 0 | 3rd Party Duct | 0 | 3rd Party Duct | 0
| Road Cut | 0 | Road Cut | 0 | Road Cut | 0
| Drilling | 0 | Drilling | 0 | Drilling | 0
| Trench | 0 | Trench | 0 | Trench | 0
| Aerial | 0 | Aerial | 0 | Aerial | 0
| Civil & 3rd Party Distance | 0 | Civil & 3rd Party Distance | 0 | Civil & 3rd Party Distance | 0
| Total Route Distance | 0 | Total Route Distance | 0 | Total Route Distance | 0
| ISP | [5 empty] | ISP Instructions and Risks
| Sewer | 0
| Stormwater | 0
| Total Focus | 0
| LA Duct | 0
| Splicing on Existing Cable | 0
| Total Existing | 0
| 3rd Party Duct | 0
| Tar | 0
| Paving | 14
| Concrete | 0
| Drilling | 0
| Trench | 8
| Aerial | 0
| In Building Conduits | 37
| Civil & 3rd Party Distance | 59
| Total Route Distance | 59
Notes
Date:
Note on B4: George Fevrier: This is the Project Number: eg: COJAADA005
Note on B5: George Fevrier: This is the Circuit ID: eg: 57G0000452

## Infra Build BOQ
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 | [13 empty] | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| OSP Planner | LUCAS | Planning Date |  | 2023-08-22
| ISP Planner | LUCAS | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
| Surveyor | VICTOR
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | QTY CIVIL | Total (OSP) | JETTING | Total Jetting | DRILLING | Total | RE-INSTATEMENT | Total | FLOATING | Total | FOCUS INSTALLATION | Total | SPLICING | Total | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT |  |  |  | 850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 1 | 850 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 | 850 |  |  | 1 | 850 |  |  | 1 | 850 |  |  | 1 | 850 |  |  | 0
| 2 | TRENCHING |  |  |  | 762.3
| 2.01 | Excavation of trial pit (400mm width x 1000mm length x 1200mm depth) | m | 96 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.02 | Excavation of drill pit (1500mm width x 1500mm length x 1500mm depth) | m | 185 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.03 | Excavation of trial pit to prove municipal duct (400mm width x 1000mm Length x 700mm depth) | m | 60.23 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.04 | Excavation of trial pit to prove municipal duct (400mm width x 1000mm Length x 1000mm depth) | m | 86.04 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.05 | ISP - Excavation and backfilling of trench in normal soil Pickable (300 mm width x 1000 mm depth) | m | 68.75 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.06 | ISP - Excavation and backfilling of trench in normal soil Pickable (300 mm width x 400 mm depth) (For access layer / FTTH layer in MDU's) | m | 34.65 | 22 | 762.3 | [13 empty] | 22 | 762.3 |  |  | 22 | 762.3 |  |  | 22 | 762.3 |  |  | 22 | 762.3 |  |  | 0
| 2.07 | ISP - Excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 81.2 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.08 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 31.78 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.09 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 84.75 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.1 | ISP - Excavation and backfilling of trench in normal soil - 300mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 121.36 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.11 | ISP - Excavation and backfilling of trench in normal soil - 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 260.06 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.12 | ISP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 400mm depth) | m | 256.8 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.13 | ISP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (450mm width x 1000mm depth) | m | 963 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.14 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 400mm depth) | m | 31.78 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.15 | ISP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping 450mm width x 1000mm depth | m | 143.57 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.16 | ISP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping 300mm width x 400mm depth (For access layer / FTTH layer in MDU's) | m | 34.2 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.17 | OSP - Excavation and Backfilling of trench in normal soil Pickable (300 mm width x 700 mm depth) | m | 60.23 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.18 | OSP - Excavation and Backfilling of trench in normal soil Pickable (450 mm width x 1000 mm depth) | m | 129.06 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.19 | OSP - Applicable to RET Contractors only _ P&Gs: OSP - an additional R5.00 per meter when excavation and backfilling of trench in normal soil pickable (400 mm width x 700 mm depth) | m | 5 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.2 | OSP - Excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) (For access layer/FTTH layer in estates or complexes) | m | 81.2 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.21 | OSP - Excavation and backfilling of trench in normal soil - 300mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 121.36 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.22 | OSP - Excavation and backfilling of trench in normal soil - 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 260.06 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.23 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 70.63 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.24 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 132.43 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.25 | OSP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 800mm depth) | m | 273.6 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.26 | OSP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (450mm width x 1000mm depth) | m | 513 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.27 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 84.75 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.28 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 450mm width x 1000mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 158.91 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.29 | OSP - Break, excavation and backfilling of trench in hard soil (Mechanical tools required) (450mm width x 1000mm depth) | m | 158.91 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.3 | OSP - Break, excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping in hard soil (Mechanical tools required) (450mm width x 1000mm depth) | m | 161.95 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.31 | OSP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping (300mm width x 700mm depth ) | m | 67 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.32 | OSP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping (450mm width x 1000mm depth) | m | 143.57 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.33 | OSP - Excavation and Backfilling of trench in normal soil Pickable using a Tractor Loader Backhoe (TLB) (300mm width x 600 to 800mm depth) | m | 34.13 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.34 | OSP - Excavation and Backfilling of trench in Intermediate soil using a Tractor Loader Backhoe (TLB) (300mm width x 600 to 800mm depth) | m | 50.2 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.35 | OSP - Excavation and Backfilling of trench using a Compact Mechanical Trenching Machine (160mm width x 600 to 800mm depth) | m | 24.75 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.36 | OSP - Excavation and Backfilling of trench using a Compact Mechanical Trenching Machine including installation of duct in trench (160mm width x 600 to 800mm depth) | m | 30.25 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.37 | OSP - Excavation and Backfilling of trench in Intermediate soil using a Compact Mechanical Trenching Machine including installation of duct in trench (160mm width x 600 to 800mm depth) | m | 49.5 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.38 | Excavation of hard rock in trench | m³ | 867.39 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.39 | Excavation of intermediate rock in trench | m³ | 494.09 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.4 | Excavation and backfilling of trench in Hard Soil (400mm width x 700mm depth) | m | 88.35 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2 | WALLS & SPECILISED SURFACES |  |  |  | 199.5
| 2.39 | Build single brick retaining wall | m² | 350 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.4 | Build double brick retaining wall | m² | 700 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.41 | Supply and install interlocking block retaining wall | ea | 26.26 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.42 | Removal of paving /m2 (Brick paving Slabbed paving and Slasto) | m² | 28.5 | 7 | 199.5 | [13 empty] | 7 | 199.5 |  |  | 7 | 199.5 |  |  | 7 | 199.5 |  |  | 7 | 199.5 |  |  | 0
| 2.43 | Supply and install concrete slab for duct protection (300mmx700mmx50mm or as otherwise specified) | ea | 30.45 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.44 | Supply and place city duct markers including painting with yellow road marking paint | ea | 19.65 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 2.45 | DCP testing every 20m | ea | 10 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 3 | PIPES AND DUCTS |  |  |  | 147.58 | [7 empty] | 1000
| 3.01 | Install 1 x 110mm HDPE pipe in open trench | m | 3 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 3.02 | Install 1 x 50mm/40mm Aggri pipe in open trench | m | 3 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 3.03 | Install 2 x 110mm HDPE pipe in open trench | m | 6 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 3.04 | Supply and install 110mm steel pipe in open trench | m | 130 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 3.05 | Install 1/2/4/7 way 12/10 micro-duct in existing duct (110mm duct/Bosal/PVC) | m | 7.5 | 9 | 67.5 | [13 empty] | 9 | 67.5 |  |  | 9 | 67.5 |  |  | 9 | 67.5 |  |  | 9 | 67.5 |  |  | 0
| 3.06 | Install 1/2/4/7 way 12/10 micro-duct in open trench | m | 3.64 | 22 | 80.08 | [13 empty] | 22 | 80.08 |  |  | 22 | 80.08 |  |  | 22 | 80.08 |  |  | 22 | 80.08 |  |  | 0
| 3.07 | DIT (Duct Integrity Testing) per duct length Minimum rate R1000.00 or as per agreement. For ISP Only | ea | 1000 | [8 empty] | 1 | 1000 | [5 empty] | 1 | 1000 |  |  | 1 | 1000 |  |  | 1 | 1000 |  |  | 1 | 1000 |  |  | 0
| 3.08 | DIT (Duct Integrity Testing) per duct length for entire route. Minimum rate R1000.00 or as per rate per m | ea | 0.65 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 4 | BEDDING PADDING AND BACKFILLING |  |  |  | 0
| 4.01 | Supply and install bedding and padding | m | 8 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 4.02 | Supply and install of import backfilling material | m³ | 264 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 4.03 | Stabilizing backfilling material with cement (G2 Mix) | m³ | 180 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 4.04 | Concrete encasement of pipes (labour and 20 mpa concrete) 300mm width x 220mm depth | m | 122.95 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 4.05 | Supply and install cast concrete slab for duct protection 300mm width x 100mm depth | m | 70 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 4.06 | Concrete encasement of pipes (labour and 20 mpa concrete) 100mm width x 100mm depth | m | 24.18 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5 | SURFACE RE-INSTATEMENTS |  |  |  | 0 | [5 empty] | 665
| 5.01 | Re-instatement of asphalt and crusher 300mm width ≤ 100mm thick | m | 172.97 | [7 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5,01,1 | ISP Trenching Capping | m | 36.89 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5.02 | Re-instatement of concrete (18Mpa) 300mm width ≤ 100mm thick | m | 94.76 | [7 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5.03 | Re-instatement of asphalt ≤ 100mm thick | m² | 318.72 | [7 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5.04 | Re-instatement of asphalt or concrete (And crusher) (20 Mpa) 300mm width >100mm thick - ROAD | m | 297.5 | [6 empty] | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5.05 | Surface re-instatement - tiles paving inter locking brick and Slabbed paving | m² | 95 | [6 empty] | 7 | 665 | [7 empty] | 7 | 665 |  |  | 7 | 665 |  |  | 7 | 665 |  |  | 7 | 665 |  |  | 0
| 5.06 | Re-instatement of grass | m | 20 | [7 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 5.07 | Re-establishment of vegetation landscaping and seedlings | m | 48 | [7 empty] | 0 | [7 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6 | MANHOLES |  |  |  | 0
| 6.01 | Supply and install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 2287.7 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.02 | Install large concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x1000mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1452.57 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.03 | Install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1187.7 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6,03,1 | Reposition or Install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1187.7 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.04 | Supply and install large concrete precast manhole including rings with knockouts and precast cover (Internal diameter 1000mm x 1000mm depth wall thickness 65mm to 75mm) | ea | 3120 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.05 | Install precast concrete flatpack manhole (605mm x 545mm x 700 mm) | ea | 545.45 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.06 | Construct single skin clay brick and mortar manhole including cover slab (600mm length x 600mm width x 600mm depth - inside dimensions) | ea | 1383.32 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.07 | Construct double skin clay brick and mortar manhole including frame and cover (1000mm length x 1000mm width x 1000mm depth - inside dimensions) | ea | 4286 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.08 | Install Polymer 500x500mm Manhole | ea | 545.45 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6,08,1 | Reposition or Install Polymer 500x500mm Manhole | ea | 545.45 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.09 | Install 350mm x350mm Toby box | ea | 160 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.1 | Install 250x230x300mm Toby Box | ea | 160 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.11 | Install Smartlock 400x400mm Manhole | ea | 123.43 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.12 | Install Smartlock 400x600mm Manhole | ea | 164.75 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.13 | Install Medium Duty 600x600mm Manhole (DMC) | ea | 504.69 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.14 | Install Medium Duty 900x900mm Manhole (DMC) | ea | 599.12 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.15 | Supply and Install Replacement 3rd Party Manhole concrete lid (490-560mm Light duty lid) | ea | 255 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.16 | Supply and Install Replacement 3rd Party Manhole coping and concrete lid (860mm Ø x 75mm depth with 490 mm hole and 560mm light duty lid) | ea | 520 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.17 | Supply and Install Cabinet Plinth - LA Spec1, 2.45m x1.76m x 0.23m | ea | 4899.96 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.18 | Supply and Install Cabinet Plinth - LA Spec2, 1500x950x100, Install Cabinet Base & Cabinet | ea | 2869 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.19 | Install LA 23U cabinet on Existing Plinth | ea | 750 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.2 | Supply and install of 3 phase lockable meter box and electrical cabling | ea | 5250 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.21 | Install iMonnit Equipment in Indoor POP | ea |  |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 6.22 | Install iMonnit Equipment in Street Cabinet POP | ea |  |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7 | SPECIALISED CROSSINGS | [7 empty] | 0
| 7.01 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in normal soil (LA supply the Drill pipe and do the scanning) | m | 250 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.02 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in normal soil (SP supply the Drill pipe and do his own scanning) | m | 500 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.03 | Thrust boring/directional drilling and installation of 2 x 110mm HDPE duct Class 6 or higher in normal soil | m | 900 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.04 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in intermediate rock | m | 730 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.05 | Thrust boring/directional drilling and installation of 2 x 110mm HDPE duct Class 6 or higher in intermediate rock | m | 1200 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.06 | Supply and install of pipe and accessories for 1-way bridge attachment for bridge crossing | m | 449.2 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.07 | Scanning For Directional Drilling | m | 77.5 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 7.08 | Soil displacement / Thrust boring and installation of 1 x 50/43mm sub duct Class 6 or higher in normal or intermediate soil | m | 72 |  |  |  |  | 0 | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8 | IN-BUILDING INSTALLATION |  |  |  | 596.58
| 8.01 | External wall core drilling - diameter 50mm - 130mm (Building outer wall ≤250mm wide) | ea | 200 | 1 | 200 | [13 empty] | 1 | 200 |  |  | 1 | 200 |  |  | 1 | 200 |  |  | 1 | 200 |  |  | 0
| 8.02 | External wall core drilling - diameter >150mm (Building outer wall > 250mm wide) | ea | 480 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.03 | Core drilling (Concrete apron 300mm deep x 75mm diameter) | ea | 450 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.04 | Supply and install 25mm PVC duct against building/Trunking | m | 16.39 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.05 | Supply and install 25mm Galvanised Bosal Pipe duct against building | m | 27.79 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.06 | Supply and install 50mm galvanised bosal against building (2 storey high) | m | 82.3 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.07 | Supply and Install 50mm galvanised bosal against building (exceeding 2 storey high) | m | 102.47 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.08 | Supply and Install 90° Bosal Bend | ea | 130 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.09 | Supply and Install Coupling 50mm Bosal | ea | 50 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.1 | Supply and install 50mm pvc pipe (2 storey high) | m | 40 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.11 | Supply and install 50mm pvc pipe (exceeding 2 storey high) | m | 60 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.12 | Supply and install 75mm x 50mm galvanised trunking against building (2 storey high) | m | 61.17 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.13 | Supply and install 75mm x 50mm galvanised trunking against building (exceeding 2 storey high) | m | 86.17 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.14 | Supply paint and Preparation and painting of PVC duct/square trunking/bosal | m | 14.5 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.15 | Supply and install cable trays (RF HD 225mm) | m | 200 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.16 | Supply and install cable trays (Wire Basket 100mm Wide 75mm Depth) including bends and splices | m | 165 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.17 | Supply and install welded wired mesh cable tray (WWHD 100mm) including joiner set | m | 205 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.18 | Supply and install welded wired mesh cable tray (WWHD 200mm) including joiner set | m | 225 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.19 | Install optic cable onto cable trays, risers or in ceilings | m | 6.5 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.2 | Install 40mm, 7 way, 4 way, 2 way or 1 way duct onto cable tray, riser, in ceiling or under false floor | m | 6.5 | 28 | 182 | [13 empty] | 28 | 182 |  |  | 28 | 182 |  |  | 28 | 182 |  |  | 28 | 182 |  |  | 0
| 8.21 | Install PVC duct / sprague / square trunking / bosal against wall, building etc including the drilling of walls | m | 16.39 | 9 | 147.51 | [13 empty] | 9 | 147.51 |  |  | 9 | 147.51 |  |  | 9 | 147.51 |  |  | 9 | 147.51 |  |  | 0
| 8.22 | Install PVC duct / against wall, building etc including drills (single drill per anchor point every 1m) _ HV-MDU Application | m | 12.09 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.23 | ISP - Cut and seal gland plate | ea | 50.5 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.24 | Install - Slack Box/Junction Box/Home Pass Point MPEbox(J1) | ea | 67.07 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.25 | ISP - Supply and install fibre glass draw/junction box | ea | 350 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.26 | ISP - Supply and install concrete entry block | ea | 250 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.27 | ISP - Supply and install flex pipe and gland onto bosal and gland plate. (Located where feeders enter BTS site) | ea | 122.98 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.28 | Install 50mm Stainless Steel Pipe | m | 18 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.29 | Supply and Install 6U x 400+200mm -19" Wall mount Swing Cabinet | ea | 1953.5 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.3 | Supply and Install 9U x 400+200mm -19" Wall mount Swing Cabinet | ea | 2566 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.31 | Install up to 12 U Cabinet | ea | 500 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.32 | Prepare and install Fibre Termination Point 4 / 12 / 24 way Wall Mount Distribution Box including accessories | ea | 67.07 | 1 | 67.07 | [13 empty] | 1 | 67.07 |  |  | 1 | 67.07 |  |  | 1 | 67.07 |  |  | 1 | 67.07 |  |  | 0
| 8.33 | Supply and Label ODF and Cables on ISP Installations | ea | 90.91 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.34 | Supply and Label Micro Duct on ISP Installations (Heat Shrink, Arrow Label holders, Brother Tape & Cable Ties) | ea | 90.91 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 8.35 | Supply and Label Micro Duct on ISP Installations (Brother Tape on the 1 Way) | ea | 25 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9 | CABLE FLOATING AND HAULING |  |  |  | 333 | [7 empty] | 0
| 9.01 | Install 2 / 4 / 6 / 8 / 12 / 24 Fibre Optic Drop Cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5 | 74 | 333 | [13 empty] | 74 | 333 |  |  | 74 | 333 |  |  | 74 | 333 |  |  | 74 | 333 |  |  | 0
| 9.02 | Floating of Focus/CST Optic fibre cable in 40mm HDPE duct | m | 5.5 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9.03 | Floating of Micro cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9.04 | Pulling of slack between manholes (existing cables Measurement of slack in manhole only) | m | 3 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9.05 | Installation and pulling/Hauling of fibre optical cable in EXISTING ducts | m | 9.98 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9.06 | Installation and pulling/Hauling of fibre optical cable in NEW ducts | m | 9.71 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9.07 | Recovery of cable from existing ducts and sewer | m | 3 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 9.08 | Supply and Label ODF and Cables | ea | 90.91 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 10 | FIBRE TERMINATION (JOINTING / SPLICE OF FIBRE IN MANHOLES OPTIVAL DISTRIBUTION FRAMES AND PATCH PANELS) | [11 empty] | 0 |  |  |  | 170
| 10.01 | Supply and Label ODF and Cables | ea | 90.91 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 10.02 | Prepare and splice single fibre in existing patch panel joint or ODF (per splice) | ea | 85 | [12 empty] | 2 | 170 |  | 2 | 170 |  |  | 2 | 170 |  |  | 2 | 170 |  |  | 2 | 170 |  |  | 0
| 10.03 | Prepare cable ends and joint for splicing (Loop only) | ea | 400 | [13 empty] | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 10.04 | Prepare and Install Patch Panel/FMT including the preparation of splitters | ea | 400 | [13 empty] | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 11 | FIBRE CABLE TEST PER STRAND AND ACCESSORIES | [11 empty] | 0 |  |  |  | 0
| 11.01 | Pre haul optic fibre cable test (per fibre) | ea | 12 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 11.02 | Post haul optic fibre cable test (per fibre) | ea | 15 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 11.03 | Relay section test bi-directional OTDR including report | ea | 25 | [13 empty] | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 11.04 | Relay section test- Bi-directional Power And Light source testing and fibre verification including report | ea | 20 | [13 empty] | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 11.05 | Call Out fee per hour | ea | 350 | [9 empty] | 0 | [5 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12 | FOCUS INSTALLATIONS |  |  |  | 0 |  | 0 | [7 empty] | 0
| 12.01 | Sewer Manhole Wall Core drilling -120mm | ea | 145.35 | 0 | [14 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.02 | Installation and pulling/Hauling of fibre optical cable (FOCUS) | m | 9.37 | [11 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.03 | Installation of Entry and Exit manifold including clips | ea | 946.8 | [10 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.04 | Installation of Entry or Exit manifold including clips | ea | 771.01 | [10 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.05 | Installation of Straight manifold | ea | 682.35 | [10 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.06 | Repair of Benching or Manhole Floor per manhole | ea | 276 | [11 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.07 | Storm water Slot Cutting | ea | 425.96 | [10 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.08 | Installation of Storm Water Entry and Exit | ea | 586.95 | [10 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.09 | Installation of Storm Water Entry or Exit | ea | 478 | [10 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.1 | CCTV Survey Pre Installation | m | 14.38 | [11 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.11 | CCTV Survey Post Installation | m | 11.5 | [11 empty] | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.12 | High Pressure Jetting -Sewer | m | 25.88 |  |  |  | 0 | [11 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.13 | High Pressure Jetting-StormWater | m | 51.75 |  |  |  | 0 | [11 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.14 | Over pumping ≤300mm pipe pumping distance not exceeding 150m | hour | 506 |  |  |  | 0 | [11 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 12.15 | Sewer sand Bagging per manhole | ea | 23 |  |  |  | 0 | [11 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13 | AERIAL LINE CABLE |  |  |  | 0
| 13.01 | Survey, Dig / Drill and Plant 7.2 m Pole (100mm-125mm) (Hole 350mm Ø x 1200mm deep) | ea | 210.57 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.02 | Survey, Dig / Drill and Plant 9 m Pole (125mm-150mm) (Hole 350mm Ø x 1500mm deep) | ea | 252.69 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.03 | Survey Dig Plant and Fit All Sizes Struts Complete To Poles | ea | 159.18 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.04 | Survey, Drill or Dig and Plant Stays or Stay Plates and Rods As Surveyed 12mm Stay Hole (350mm X 350mm X 1000mm Deep) Including Stay Wire 7 x 1.7mm, Guy Grip,Bracket 45DEG for Stay Wire Grip and Duckbill Stay Anchor | ea | 186.55 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.05 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead End FDE 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | ea | 71.07 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.06 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead End FDE 415/459 for ADSS 10.54-11.66mm (48 & 72 Fibre) | ea | 75.07 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.07 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead end FDE 616/680 for ADSS 15.6-17.27mm (144 Fibre) | ea | 79.07 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.08 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | ea | 45.12 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.09 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 398/425 for ADSS 10.1-10.8mm (48 Fibre) | ea | 55.12 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.1 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 426/455 for ADSS 10.8-11.5mm (72 Fibre) | ea | 65.12 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.11 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 595/630 for ADSS 15.11-16.0mm (144 Fibre) | ea | 75.12 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.12 | Erecting Hauling Tensioning of Fibre Optical Cable on Overhead Cable Route (All Sizes) | m | 4.57 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.13 | Concreting of Poles or Strut | ea | 228 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.14 | Concreting of All size Stays | ea | 258 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.15 | Install Pole Mounted Optic Fibre Slack Box | ea | 90 | 0 | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 13.16 | Quote to Auger to Plant Poles |  |  |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14 | FTTH FULL TURNKEY PRICING |  |  |  | 0
| 14.01 | Price1A: R 3100.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) | ea | 3100 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.02 | Price1B: R 3100.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) | ea | 3100 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.03 | Price2: R 3100.00 per Demand Point – payable for a NAP/Drop Point (Manhole outside the Gated SDU and MDU Property) | ea | 3100 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.04 | Price3: R 3100.00 – payable for a NAP/Drop Point outside a business property | ea | 3100 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.05 | Price9A: R 2650.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) Civil and Duct works only | ea | 2650 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.06 | Price9B: R 2650.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) Civil and Duct works only | ea | 2650 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.07 | Price10A: R 450.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) Fibre Works only | ea | 450 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.08 | Price10B: R 450.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) Fibre Works only | ea | 450 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.09 | Price4A: R 1800.00 per DP – payable for a MDU complex | ea | 1800 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.1 | Price4B: R 1800.00 per DP – payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 1800 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14,10,1 | Price4C: R 200.00 per DP – Survey and Planning : payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 200 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14,10,2 | Price4D: R 1600.00 per DP – Build Only : payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 1600 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.11 | Price5: R 2800.00 per DP – payable for a gated SDU complex where trenching is required | ea | 2800 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.12 | Price6: R 3000.00 per DP – payable for a complex not P4 or P5 e.g. forms of trench in a townhouse complex | ea | 3000 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.13 | Price7: R 900.00 per FTB – payable per MDU Last Drop Completed | ea | 900 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 14.14 | Price8: R 1 500.00 per FTB – payable per SDU Last Drop Completed | ea | 1500 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 15 | AS-BUILT DOCUMENTATION |  |  |  | 1000
| 15.01 | Complete ISP as-built documents | ea | 1000 | 1 | 1000 | [13 empty] | 1 | 1000 |  |  | 1 | 1000 |  |  | 1 | 1000 |  |  | 1 | 1000 |  |  | 0
| 15.02 | Complete OSP as-built information | ea | 1000 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 15.03 | Complete ISP as-built documents (FTTX) | ea | 250 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16 | ADDITIONAL |  |  |  | 500
| 16.01 | Portable toilet hire | per day | 130 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.02 | Removal of Waste Material | m³ | 150 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.03 | Sand Bags (bag purchase & filling with sand) | ea | 20 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.04 | Clean 3rd party Manhole and correctly manage cable per manhole | ea | 40 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.05 | Safety File | ea | 500 | 1 | 500 | [13 empty] | 1 | 500 |  |  | 1 | 500 |  |  | 1 | 500 |  |  | 1 | 500 |  |  | 0
| 16.06 | Bush Cutting | m | 2.8 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.07 | Company Contribution of 30% of The Local Labour Cost @ R250 per person/day as Requested By Local Councillors | Man/day | 75 | [15 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.07.1 | Link Africa Contribution of 30% of The Local CLO Cost @ R500 per person/day as Requested By Local Councillors | Man/day | 150 | [15 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.08 | Abseiling | per day | 4500 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.09 | Cherry Picker (Quote) | per day | 3500 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
| 16.1 | Full Turnkey Drop Cable installation by Contractor in Connected Building | Per Drop | 9480 |  | 0 | [13 empty] | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
|  |  |  | Total |  | 4388.96 |  | 0 |  | 0 |  | 665 |  | 1000 |  | 0 |  | 170 |  |  | 6223.96 |  |  |  | 6223.96 |  |  |  | 6223.96 |  |  |  | 6223.96 |  |  | 0
[19 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | -6223.96
[19 empty] | VARIATION ORDER % SI 01 |  | 0% |  | VARIATION ORDER % SI 02 |  | 0% |  | VARIATION ORDER % SI 03 |  | 0% |  | VARIATION ORDER % SI 04 |  | 0% |  | AS BUILD vs PO % | -100%
|  | Services Cost |  |  |  | 6223.96
|  | Free Issue Materials |  |  |  | 1321.495
|  | Project Cost |  |  |  | 7545.455
Note on C75: Not to form part of EXE, will be done on VO based on site instruction from PL.

## MATERIAL REQUEST
77G0056723 / 77G0056723
Project No. / Planning Ref | 77G0056723 / 77G0056723 |  | ISP SITE ID |  | G1VDA066
Customer Name | VODACOM |  | Affected Region/s |  | WITKOPPEN RD
Project Leader | 0 |  | Planning Date |  | 2023-08-22
Contractor | CONTRACTOR NAME |  | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
MATERIALS | [6 empty] | VO 1 |  |  |  | VO 2 |  |  |  | VO 3 |  |  |  | VO 4
CATERGORY | STOCK CODE | DESCRIPTION | UNIT | QTY | COST RATE | COST | QTY | ACCUMULATED QTY | COST | COMMENTS | QTY | ACCUMULATED QTY | COST | COMMENTS | QTY | ACCUMULATED QTY | COST | COMMENTS | QTY | ACCUMULATED QTY | COST | COMMENTS
CABLE | FR-ISS 2 | 144 CST Optic Fibre Optical Cable | m | 0 | 29.9 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 3 | 144 FOCUS Optic Fibre Cable | m | 0 | 93.43 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 4 | 288 FOCUS Optic Fibre Cable | m | 0 | 110.56 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 117 | 10m Wall Box Cable for FTTH (2 x LC/APC connectors) | each | 0 | 309.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 118 | 30m Wall Box Cable for FTTH (2 x LC/APC connectors) | each | 0 | 412.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 120 | 70m Wall Box Cable for FTTH (2 x LC/APC connectors) | each | 0 | 618.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 121 | 100m Wall Box Cable for FTTH (2 x LC/APC connectors) | each | 0 | 773 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 122 | 40m Drop Cable for FTTH (1 x LC/APC connectors both ends) | each |  | 540 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 123 | 70m Drop Cable for FTTH (1 x LC/APC connectors both ends) | each |  | 753 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 124 | 120m Drop Cable for FTTH (1 x LC/APC connectors both ends) | each |  | 1108 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 182 | 2 Fibre G657A2 Dual Drop Cable - 3.8mm | m | 74 | 2.65 | 196.1 |  | 74 | 196.1 |  |  | 74 | 196.1 |  |  | 74 | 196.1 |  |  | 74 | 196.1
CABLE | FR-ISS 183 | 4 Fibre G657A2 Dual Drop Cable - 3.8mm | m | 0 | 2.85 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 184 | 6 Fibre G657A2 Dual Drop Cable - 3.8mm | m | 0 | 3.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 185 | 8 Fibre G657A2 Dual Drop Cable - 3.8mm | m | 0 | 4.18 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 186 | 12 Fibre G657A2 Dual Drop Cable - 3.8mm | m | 0 | 5.45 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 187 | 24 Fibre G657A2 (200um) Dual Drop Cable - 4.0mm | m | 0 | 11.41 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 114 | 96 Core Micro cable | m | 0 | 29 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 6 | 72 Core Micro cable | m | 0 | 18 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 7 | 48 Core Micro cable | m | 0 | 11.2 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS4F | 4 Core Aerial Cable (ADSS) - Drop Cable | m | 0 | 7.44 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS8F | 8 Core Aerial Cable (ADSS) - Drop Cable | m | 0 | 8.21 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS12F | 12 Core Aerial Cable (ADSS) | m | 0 | 9.46 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS24F | 24 Core Aerial Cable (ADSS) | m | 0 | 12.48 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS48F | 48 Core Aerial Cable (ADSS) | m | 0 | 28.45 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS72F | 72 Core Aerial Cable (ADSS) | m | 0 | 34 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | ADSS144F | 144 Core Aerial Cable (ADSS) | m | 0 | 38.34 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 112 | 24 Core Micro cable | m | 0 | 7.33 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 113 | 12 Core Micro cable | m | 0 | 6.11 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 69 | 144 Core Micro Cable | m | 0 | 31.82 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
CABLE | FR-ISS 115 | 288 Core Micro Cable | m | 0 | 90.22 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | 1WAYPIPE | 1 way 14/10 Micro Duct | m | 61.95 | 5.2 | 322.14 |  | 61.95 | 322.14 |  |  | 61.95 | 322.14 |  |  | 61.95 | 322.14 |  |  | 61.95 | 322.14
DUCT | FR-ISS 125 | 2 way 14/10 Micro Duct | m | 0 | 13.65 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 126 | 4 way 14/10 micro-duct | m | 0 | 22.64 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 127 | 7 way 14/10 micro-duct | m | 0 | 27.92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | 2WAYPIPE | 2 way 12/10 Micro Duct | m | 0 | 8.93 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | 4WAYPIPE | 4 way 12/10 micro-duct | m | 0 | 15.66 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | 7WAYPIPE | 7 way 12/10 micro-duct | m | 0 | 21.23 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 54 | 12/10 Straight connector coupler | each |  | 18 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | DUCT1210 A | Micro duct High Pressure Couplers | each |  | 16.59 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | DUCT1210 B | Micro duct High Pressure End Caps | each |  | 13.77 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 49 | Micro duct Dust covers | each |  | 0.25 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | DUCT1410 | Duct Connectors 14/10 | each |  | 18.75 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | DUCT1410 B | 14/10mm Microduct High Pressure End Caps | each |  | 21.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 51 | 14/10 Micro duct Dust covers | each |  | 1.45 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | RED002 | Reducers 14/10 TO 12/10 | each |  | 28.49 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | Duct110 | 110mm HDPE pipe | m | 0 | 24.2 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | DUCT110HDPE | 110MM OD HDPE PE100 PN10 SDR17 PIPE (Drill Pipe) | m | 0 | 76 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | DUCT75HDPE | 75MM OD HDPE PE100 PN10 SDR17 PIPE (Drill Pipe) | m |  | 62.35 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 46 | 50/43mm Sub Duct (Aggri) | m | 0 | 30.59 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 55 | 40/34mm Sub Duct (Aggri) | m | 0 | 8.9 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 52 | Trench Warning Tape | m | 22 | 1 | 22 |  | 22 | 22 |  |  | 22 | 22 |  |  | 22 | 22 |  |  | 22 | 22
DUCT | FR-ISS 90 | 16/16 Square Trunking (1way) | m |  | 11.87 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 91 | 16/16 T-ends | each |  | 2.67 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 160 | 16x16mm External angle | each |  | 4.52 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 161 | 16x16mm Internal angle | each |  | 13.48 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 162 | 16x16mm Flat angle | each |  | 4.15 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 163 | 16x16mm Stopend | each |  | 7.83 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 164 | 16x16mm Straight Joint | each |  | 6.53 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 92 | 16/40 Square Trunking (2way) | m |  | 24.8 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 93 | 16/40 T-ends | each |  | 13 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 94 | 16/40 end caps | each |  | 9.1 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 165 | 25 x 25 mm Square trunking | m | 3 | 25 | 75 |  | 3 | 75 |  |  | 3 | 75 |  |  | 3 | 75 |  |  | 3 | 75
DUCT | FR-ISS 166 | 25 x 25 mm Tee Unit | each |  | 12.63 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 167 | 25 x 25 mm External angle | each |  | 9.14 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 168 | 25 x 25 mm Internal angle | each |  | 8.9 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 169 | 25 x 25 mm Flat angle | each |  | 9.02 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 170 | 25 x 25 mm Stopend | each |  | 9.8 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 171 | 25 x 25 mm Straight Joint | each |  | 8.8 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | CONPVC | 25 mm PVC duct | m | 6 | 3.8 | 22.8 |  | 6 | 22.8 |  |  | 6 | 22.8 |  |  | 6 | 22.8 |  |  | 6 | 22.8
DUCT | FR-ISS 71 | 25 mm PVC Couplers | each | 1.5 | 0.83 | 1.245 |  | 1.5 | 1.245 |  |  | 1.5 | 1.245 |  |  | 1.5 | 1.245 |  |  | 1.5 | 1.245
DUCT | FR-ISS 72 | 25 mm PVC Bends | each |  | 12.3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 73 | 25 mm Junction Boxes | each |  | 4.84 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 74 | 25 mm Male terminator | each |  | 1.84 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | SADPVC | 25 mm PVC Saddles | each | 6 | 1.11 | 6.66 |  | 6 | 6.66 |  |  | 6 | 6.66 |  |  | 6 | 6.66 |  |  | 6 | 6.66
DUCT | FR-ISS 76 | 25 mm Sprague | m | 0 | 5.96 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 77 | 40 x 40 mm Square trunking (4way) | m |  | 35 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 78 | 40 x 40 mm External angle | each |  | 5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 79 | 40 x 40 mm Internal angle | each |  | 16.36 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 80 | 40 x 40 mm Flat angle | each |  | 4.9 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 81 | 40 x 40 mm Tee Unit | each |  | 13.65 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 82 | 40 x 40 mm Stopend | each |  | 9.09 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 83 | 40 x 40 mm Straight Joint | each |  | 8.09 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 95 | 50 mm PVC duct | m |  | 87.57 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 96 | 50 mm PVC Couplers | each |  | 7.53 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 97 | 50 mm PVC Bends | each |  | 35.63 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 98 | 50 mm PVC Junction Boxes | each |  | 58.48 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 99 | 50 mm PVC Male terminator | each |  | 16.4 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 100 | 50 mm PVC Saddles | each |  | 9.55 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 101 | 50 mm PVC Sprague | m |  | 22.67 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 172 | 50 mm Galvanised Bosal Pipe | m |  | 63.15 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 173 | 50 mm Galvanised Bosal Straight Couplers | each |  | 50.73 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 174 | 50 mm Galvanised Bosal 90° Bends | each |  | 60 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 175 | Galvanised Junction Boxes (305mm x 305mm x 100mm) | each |  | 635 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 176 | 50 mm Galvanised Bosal Male Adapter (Terminator) | each |  | 110 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 177 | 50 mm Galvanised Saddles | each |  | 3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
DUCT | FR-ISS 178 | 50 mm Galvanised Sprague | m |  | 385.25 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 146 | 7.2 m Wooden Pole (100mm to 125mm) | each | 0 | 781.2 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 147 | 9m Wooden Pole (125mm to 150mm) | each | 0 | 1484.3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 111 | 12m Wooden Pole (125mm to 150mm) | each |  | 1485.3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 179 | 7 m Concrete Pole (160mm to 265mm) | each |  | 1999 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 180 | 9 m Concrete Pole (160mm to 295mm) | each |  | 3199 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 181 | 11 m Concrete Pole (160mm to 325mm) | each |  | 4999 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 188 | 7.5 m Composite Pole (108mm) - Basic Light duty | each |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 189 | 9 m Composite Pole (138mm) - Basic Meduim duty | each |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POLE | FR-ISS 190 | 11 m Composite Pole (170mm) - Basic Heavy duty | each |  | 4715.6 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FR-ISS 148B | Stay Rod 1830 X 16MM Complete (with Adjustable Stay Rod Assembly) | each |  | 554.39 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | A-88-DB1 | Duckbill Stay Anchor | each | 0 | 265.15 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FR-ISS 149A | Stay Guard (Chevron) | each | 0 | 139.78 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | STAYWIRE 7/1.70 | Stay Wire 7 x 1.7mm | m | 0 | 7.39 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | TGG 201 | Guy Grip for 7/1.7mm Stay Wire | each | 0 | 82.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | TGGB-45 | Bracket 45DEG for Stay Wire Grip | each | 0 | 62.18 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | HB1-10-MI | Suspension Hook Single | each | 0 | 17.88 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | HB2-10-MI | Suspension Hook Double | each | 0 | 29.06 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | M12X220BHT120HD | M12X220 HDG 120mm Thread Bolt with Nut & Washer | each | 0 | 34.78 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FDE 375/414 | Dead End FDE 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | each | 0 | 79.94 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FDE 415/459 | Dead End FDE 415/459 for ADSS 10.54-11.66mm (48 & 72 Fibre) | each | 0 | 84.29 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FDE 616/680 | Dead end FDE 616/680 for ADSS 15.6-17.27mm (144 Fibre) | each | 0 | 109.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FOT 375/414 | Tangent Support FOT 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | each | 0 | 68.51 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FOT 398/425 | Tangent Support FOT 398/425 for ADSS 10.1-10.8mm (48 Fibre) | each | 0 | 78.43 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FOT 426/455 | Tangent Support FOT 426/455 for ADSS 10.8-11.5mm (72 Fibre) | each | 0 | 107.27 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FOT 595/630 | Tangent Support FOT 595/630 for ADSS 15.11-16.0mm (144 Fibre) | each | 0 | 136.69 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | FIBRE-SLACK-BIN | Pole Mounted Optic Fibre Slack Box | each | 0 | 706.03 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | PSB300P | Figure 8 Slack brackets for Aerial Cable | each |  | 144.35 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | BLC136SA | 19mm Strapping (covers 18 Slack brackets) | m | 0 | 27.15 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
AERIAL | BLC956SA | 19mm Buckles (Supplied in boxes of 100) | each | 0 | 2.27 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
BOXES | FR-ISS 68 | ALLBRO UTILEC BOX SCREW LID 110X110X90MM UT2 | each |  | 165 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
BOXES | FR-ISS 67 | ALLBRO UTILEC BOX SCREW LID 310 x 210 x 125 mm Allbro UT7 Slide | each |  | 505 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
BOXES | FR-ISS 84 | ALLBRO 87 x 87 x 55 mm Allbro MPEbox (J1) Junction Box (HDP) | each |  | 72.89 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 25 | Manhole lids with Frames | each |  | 953.92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 26 | Manhole lids only | each | 0 | 1660 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 27 | Manhole lid Key | each |  | 380 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 28 | 1130mm coping concrete | each |  | 715 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | MANH05 | Polymer 500x500 drop-in Manhole complete | each | 0 | 2200 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 57 | 350X350 TOBY BOX | each | 0 | 435 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 103 | 250x230x300mm Toby Box | each | 0 | 198 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 104 (SL002) | Smartlock - RHI-NODE 400 STD | each | 0 | 585 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 105 (SL003) | Smartlock - RHI-NODE 400 200mm (Extension only) | each | 0 | 290 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 106 | Medium Duty 600x600mm Manhole (DMC) | each | 0 | 4495 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 107 | Medium Duty 900x900mm Manhole (DMC) | each | 0 | 8035.29 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 50 | LA 500x500 Slack Brackets | each |  | 90 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | COP001 | Prefab 1000mm rnd x 500mm w/1 x slack bracket | each |  | 31 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 88 | Precast concrete flatpack manhole (605mm x 545mm x 700 mm) | each |  | 5348.15 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | CSLAB03 | Small concrete precast manhole including rings with knockouts and precast cover 1000mm (diameter)x500mm (Depth) | each | 0 | 2153.92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
MANHOLE | FR-ISS 102 | Large concrete precast manhole including rings with knockouts and precast cover 1000mm (diameter)x1000mm (Depth) | each | 0 | 2653.92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | DOMEFIST01 | FIST GC02 BC 06 Dome Joints | each |  | 3300 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FIST-RSKG-4b | FIST Mechanical Gel Seal - 4 port | each |  | 577.11 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | DOME48F | Joint 209B 48 splice mini joint (Shrink Seals) | each | 0 | 750 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 36 | Joint 204B 144 splice joint (Shrink Seals) | each | 0 | 1650 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 85 | Joint Tank 48 splice mini joint (Shrink Seals) | each |  | 700 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 108 | Micro Loop Joint (4 x LC/APC Pigtails and 2x LC/APC Midcouplers Only) | each | 0 | 566.96 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 109 | Micro Loop Joint (4 x LC/APC with 1:4 Splitter_Connectorized) | each |  | 707.99 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | 108 LCA KIT3 | Termination Box 4 way complete - Customer Access Box | each | 1 | 80 | 80 |  | 1 | 80 |  |  | 1 | 80 |  |  | 1 | 80 |  |  | 1 | 80
FEC & ACCESSORIES | FR-ISS 110 | 4 Fibre Wall Mount Distribution Box including accessories (FTTH Boundary Box) | each | 0 | 175 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | WALLMOUNT2 | 12 Fibre Wall Mount Distribution Box including accessories | each | 0 | 550 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | WALLMOUNT3 | 24 Fibre Wall Mount Distribution Box including accessories | each | 0 | 950 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SBOX01 | 48 Fibre Wall Mount Distribution Box including accessories | each | 0 | 1295 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SBOX02 | 96 Fibre Wall Mount Distribution Box including accessories | each | 0 | 3100 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 86 | 9U Cabinet | each |  | 2378.6 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 45 | 12U Split Cabinet | each |  | 2545 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 44 | 21U Cabinet | each |  | 9000 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 43 | 42U Cabinet (600x800) Perforated | each |  | 12118.99 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 56 | 12 Port Patch Panel | each | 0 | 850 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 58 | 24 Port Patch Panel | each | 0 | 850 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 53 | 48 Port Patch Panel | each | 0 | 1200 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 70 | 144 Patch Panel | each | 0 | 1500 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 75 | 288 Patch Panel | each | 0 | 1800 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 41 | FMT Slack Management Tray and FOMS 48F Termination Panel | each |  | 7790 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 87 | P05 1U High Density Pivot Panel incl. LC 48 pigtails Complete and 1U Panel slack drawer_1U_Telescopic | each |  | 3126.36 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PIGT06 | LC/APC Pig Tails | each | 2 | 16.95 | 33.9 |  | 2 | 33.9 |  |  | 2 | 33.9 |  |  | 2 | 33.9 |  |  | 2 | 33.9
FEC & ACCESSORIES | PIGT08 | Fibernet LC/APC 2m 9/125 UNJ. PIGTAIL LSZH G657A1 600 Micron | each |  | 27.68 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | COUP01 | Mid Coupler LC/PC Duplex Single Mode Blue | each |  | 13.4 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | COUP4 | LC/APC Mid Couplers (Duplex - Green) | each | 1 | 11.65 | 11.65 |  | 1 | 11.65 |  |  | 1 | 11.65 |  |  | 1 | 11.65 |  |  | 1 | 11.65
FEC & ACCESSORIES | COUP05 | SC/APC Mid Couplers (Simplex - Green) | each |  | 9.08 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-SC/UPC-1m-SX (SG-LB) | LC/APC to SC/UPC PATCH LEAD 1m SIMPLEX (Small Green-Large Blue) | each |  | 92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-SC/UPC-2m-SX (SG-LB) | LC/APC to SC/UPC PATCH LEAD 2m SIMPLEX (Small Green-Large Blue) | each |  | 102.35 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-SC/UPC-3m-SX (SG-LB) | LC/APC to SC/UPC PATCH LEAD 3m SIMPLEX (Small Green-Large Blue) | each |  | 82.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-SC/UPC-5m-SX (SG-LB) | LC/APC to SC/UPC PATCH LEAD 5m SIMPLEX (Small Green-Large Blue) | each |  | 121.35 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-SC/UPC-10m-SX (SG-LB) | LC/APC to SC/UPC PATCH LEAD 10m SIMPLEX (Small Green-Large Blue) | each |  | 151.85 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/APC-1m-DX (SG-SG) | LC/APC to LC/APC PATCH LEAD 1M DUPLEX (Small Green-Small Green) | each |  | 75.89 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/APC-2m-DX (SG-SG) | LC/APC to LC/APC PATCH LEAD 2M DUPLEX (Small Green-Small Green) | each |  | 106.12 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/APC-3m-DX (SG-SG) | LC/APC to LC/APC PATCH LEAD 3M DUPLEX (Small Green-Small Green) | each |  | 194.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/APC-5m-DX (SG-SG) | LC/APC to LC/APC PATCH LEAD 5M DUPLEX (Small Green-Small Green) | each |  | 255 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/APC-10m-DX (SG-SG) | LC/APC to LC/APC PATCH LEAD 10M DUPLEX (Small Green-Small Green) | each |  | 230 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/UPC-1m-DX (SG-SB) | LC/APC to LC/UPC PATCH LEAD 1M DUPLEX (Small Green-Small Blue) | each |  | 85.44 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/UPC-2m-DX (SG-SB) | LC/APC to LC/UPC PATCH LEAD 2M DUPLEX (Small Green-Small Blue) | each |  | 102.35 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/UPC-3m-DX (SG-SB) | LC/APC to LC/UPC PATCH LEAD 3M DUPLEX (Small Green-Small Blue) | each |  | 105.85 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/UPC-5m-DX (SG-SB) | LC/APC to LC/UPC PATCH LEAD 5M DUPLEX (Small Green-Small Blue) | each |  | 149.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/APC-LC/UPC-10m-DX (SG-SB) | LC/APC to LC/UPC PATCH LEAD 10M DUPLEX (Small Green-Small Blue) | each |  | 182.77 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/UPC-LC/UPC-1m-DX (SB-SB) | LC/UPC to LC/UPC PATCH LEAD 1M DUPLEX (Small Blue-Small Blue) | each |  | 95 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/UPC-LC/UPC-2m-DX (SB-SB) | LC/UPC to LC/UPC PATCH LEAD 2M DUPLEX (Small Blue-Small Blue) | each |  | 106.12 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/UPC-LC/UPC-3m-DX (SB-SB) | LC/UPC to LC/UPC PATCH LEAD 3M DUPLEX (Small Blue-Small Blue) | each |  | 113.14 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/UPC-LC/UPC-5m-DX (SB-SB) | LC/UPC to LC/UPC PATCH LEAD 5M DUPLEX (Small Blue-Small Blue) | each |  | 143 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | PATLC/UPC-LC/UPC-10m-DX (SB-SB) | LC/UPC to LC/UPC PATCH LEAD 10M DUPLEX (Small Blue-Small Blue) | each |  | 198 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLIT04 | 1:2 PLC Splitter bare 900Um tails 1m length (Un-Connectorized) | each |  | 95 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLIT01 | 1:4 PLC Splitter bare 900Um tails 1m length (Un-Connectorized) | each |  | 176 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 60 | 1:8 Splitter - Un-Connectorized | each |  | 121.9 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLIT02 | 1:16 PLC Splitter bare 900Um tails 1m length (Un-Connectorized) | each |  | 378.48 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 62 | 1:32 Splitter - Un-Connectorized | each |  | 691 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | FR-ISS 63 | 1:64 Splitter - Un-Connectorized | each |  | 1676.16 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLIT03 | 1:16 Splitter with 1M tails with LC/APC Connectors | each |  | 1235 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLPRO - 40mm (2mm) | Splice Protectors - 40mm (2mm) | each |  | 3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLPRO - 40mm (1.3mm) | Splice Protectors - 40mm (1.3mm) For CMJ & MMJ Joints | each |  | 3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FEC & ACCESSORIES | SPLTRAY | Splice Trays (for FIST GC02 BC6 Joint-SE04) | each |  | 250 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | Raisecom LANET1 | Raisecom RAX700 | each |  | 4864.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | Raisecom LANET2 | Raisecom RAX700 | each |  | 4864.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | RaisecomBRK | Raisecom Brackets | each |  | 398.93 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | Power Cord | 2M Power Cord With Dedicated Plug Top | each |  | 32.2 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | RJ45 Cord 1m | Copper Patchcord CAT5E 1M Grey | each |  | 20.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | Cage Nuts | Cage Nuts | each |  | 3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP DOM1G1310NM10kmFS | GENERIC (DOM) 1G SFP 1310NM 10KM FS | each |  | 217.92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP DOM1G1310NM20kmFS | GENERIC (DOM) 1G SFP 1310NM 20KM FS | each |  | 217.92 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP DOM1G1310NM40kmFS | GENERIC (DOM) 1G SFP 1310NM 40KM FS | each |  | 248.4 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP DOM10G1310NM80kmLR | GENERIC (DOM) 10G SFP 1310NM 80KM FS | each |  | 4740.3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP BIDI1G1550/131010KM-C | BIDI 1G 1550/1310 10KM [CLIENT] | each |  | 327.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP BIDI1G1550/131010KM-P | BX-BIDI 1G 1550/1310 10KM [POP] | each |  | 293.3 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP BIDI1G1550/131020KM-C | BIDI 1G 1550/1310 20KM [CLIENT] | each |  | 350.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP BIDI1G1550/131020KM-P | BX-BIDI 1G 1550/1310 20KM [POP] | each |  | 327.7 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP BIDI1G1550/131040KM-C | BIDI 1G 1550/1310 40KM [CLIENT] | each |  | 414 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | SFP BIDI1G1550/131040KM-P | BX-BIDI 1G 1550/1310 40KM [POP] | each |  | 414 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
ACTIVE EQUIPMENT | Media Converter | Fiber Media Converter | each |  | 850 | 0
ACTIVE EQUIPMENT | Huawei ONT | Huawei HG8310M 1Fe/Ge Port Gpon ONT | each | 1 | 550 | 550 |  | 1 | 550 |  |  | 1 | 550 |  |  | 1 | 550 |  |  | 1 | 550
POP MONITOR EQUIP | FR-ISS 128 | Monnit Link Ethernet Gateway | each |  | 6575.6 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 129 | Monnit Link GSM Gateway | each |  | 8151.22 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 130 | SIM Card (5MB month) | each |  | 800 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 131 | WIT1 Voltage Detection - 500VAC | each |  | 1824.77 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 132 | WIT1 Voltage Meter - 50VDC | each |  | 1824.77 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 133 | WIT1 Voltage Meter - 500VDC | each |  | 1824.77 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 134 | WIT1 Temperature Sensor | each |  | 1295.59 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 135 | WIT1 Open / Closed Sensor | each |  | 1559.64 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 136 | WIT1 Dry Contact Sensor | each |  | 1559.64 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 137 | Smoke Sensor W / Escape Light | each |  | 1603.38 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP MONITOR EQUIP | FR-ISS 138 | Network Configuration and Setup | each |  | 7500 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
EMS | EMS - iMonnit | EMS - iMonnit Street Cabinet POP | per site |  | 12858.98 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP CABINET | FR-ISS 139 | Street Cabinet POP (1,2m) | each |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP CABINET | FR-ISS 140 | Street Cabinet POP (2,1m) Including 3 Phase PDU | each |  | 43227.68 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP CABINET | FR-ISS 141 | 47U In Door Server Cabinet (600x800) Perforated | each |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
POP CABINET | PDU1PH | Single Phase PDU (As Per Component List) | each |  | 3500 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
RECTIFIER | FR-ISS 142 | Single Phase Rectifier Chassis (3U) (PSC06 V2) | each |  | 18261.1 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
RECTIFIER | FR-ISS 143 | Three Phase Rectifier Chassis (6U) (Flexi 1 8kw) | each |  | 35100 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
RECTIFIER | RM2048HE | RM2048HE Rectifier Modules (2kw) (3 Per Rectifier) | each |  | 3727.44 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
BATTERIES | FR-ISS 144 | 180Ah Battery (4 Per POP) | each |  |  | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
BATTERIES | FR-ISS 145 | 200Ah Battery (4 Per POP) | each |  | 4150 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | BM001 | Bend manifold 90 | each | 0 | 21.23 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | ST20319 | Straight manifold 14 purple | each | 0 | 30.5354 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | STFLAT18 | Straight manifold 18 purple | each |  | 31.2229 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | LHM001 | Left hand manifold black | each |  | 117.4598 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | RHM001 | Right hand manifold Black and purple | each |  | 117.46 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | WB20319 | Wishbone manifold purple and Black | each |  | 74.774 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | RH30821 | Resin and Hardener | each | 0 | 395.6939 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | WTRP002 | Waterplug Masterseal 505 | each | 0 | 722.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | SPAXS40 | Spax screws 75 x 40mm | each | 0 | 1.44 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | WASH001 | Washers | each | 0 | 1.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | CLIP002 | Clips | each | 0 | 7.5 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
FOCUS | MANT002 | Focus MH Tags 80 x 120mm | each | 0 | 6.38 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/3/24/13/004 | Verticasa - Mechanical Splice Holder | each | 0 | 60.34 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/3/24/13/003 | Verticasa - Riser Cable Breakout Unit 4 Port | each | 0 | 97.08 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/3/24/13/001 | Verticasa - Riser Cable Protection Cover | each | 0 | 43.88 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/3/24/01/001 | Verticasa - Tube Plugs | each |  | 13.41 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/1/11/20/001 | Verticasa - Drop Tube Int + Draw Rope | m | 0 | 7.2 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/1/24/20/003 | Flextube Indoor Cable Verticasa 48x2F G657A1 (96F) (2000m) | m | 0 | 80.32 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/1/24/20/004 | Flextube Indoor Cable Verticasa 12x2F G657A2 (24F) (2000m) | m | 0 | 30.61 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 1/1/24/20/005 | Flextube Indoor Cable Verticasa 24x2F G657A2 (48F) (2000m) | m | 0 | 49.37 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 2/1/10/20/006 | Drop Cable Internal G657A2 LSZN WHI 02F (2000m) | m |  | 3.03 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
VERTICASA | 2/1/10/20/054 | Drop Cable 4F G657A1_SM Mini Duct 3,4mm LSZH (2000m) | m |  | 5.25 | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
[6 empty] | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
[6 empty] | 0 |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
|  | TOTAL |  |  |  | 1321.495 |  | TOTAL | 1321.495 |  |  | TOTAL | 1321.495 |  |  | TOTAL | 1321.495 |  |  | TOTAL | 1321.495
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0
[7 empty] | VARIATION ORDER % SI 01 |  | 0% |  | VARIATION ORDER % SI 02 |  | 0% |  | VARIATION ORDER % SI 03 |  | 0% |  | VARIATION ORDER % SI 04 |  | 0%

## FOCUS ANCILLARIES CALC
ANCILLARIES |  |  |  | LINK |  | CONTRACTOR
Code | Description | unit | REQ
BM001 | Bend manifold 90 | each | 0
CLIP001 | Clips | each | 0 | SEWER
DOMECOMP01 | Compact Dome Joint 144F | each |  |  | Entry/Exit | Exit AND entry | straight
DOMEFIST01 | FIST Dome Joints | each |  |  | 0 | 0 | 0
DOMEFIST08 | FIST Dome Joints (GCO2-BC8-NV-ZA02) | each |  | Spax screws 75 x 40mm | 0 | 0 | 0 | 0
FIST-OSKG | FIST Mechanical Gel Seal - Oval Port | each |  | Washers | 0 | 0 | 0 | 0
FIST-RSKG-4 | FIST Mechanical Gel Seal - 4 port | each |  | Clips | 0 | 0 | 0 | 0
LHM001 | Left hand manifold black | each |  | Resin | 0 | 0 | 0 | 0
MANH02 | Manhole lids only | each |  | Waterplug | 0 | 0 | 0 | 0
Portround | Round (2) Ports Heatshrink Kits | each |  | Bend manifold 90 |  |  |  | 0
Ports | Oval (1) Ports Heatshrink Kits | each |  | Straight manifold 14 purple |  |  |  | 0
RH30821 | Resin and Hardener | each | 0
RHM001 | Right hand manifold Black and purple | each
SPAXS40 | Spax screws 75 x 40mm | each | 0 | STORM WATER
SPAXS60 | Spax screws 75 x 60mm | each |  |  | Entry/Exit | Exit AND entry | slot-cutting
SPLPRO | Splice Protectors - 40mm | each |  |  | 0 | 0 | 0
ST20319 | Straight manifold 14 purple | each | 0 | Spax screws 75 x 40mm | 0 | 0 | 0 | 0
STFLAT18 | Straight manifold 18 purple | each |  | Clips | 0 | 0 | 0 | 0
WASH001 | Washers | each | 0 | Waterplug | 0 | 0 | 0 | 0
WB20319 | Wishbone manifold purple and Black | each
WTRP001 | Waterplug | each | 0
Other : specify
Other : specify
Other : specify
CALCULATIONS
SEWER
| Entry/Exit | Exit AND entry | straight
Spax screws 75 x 40mm | 1 screw per washer, 2 screws per clip, 2 screws for manhole tage - read formula from BOQ | x2 | as per entry/exit
Washers | 4 across top + 4 across bottom | x2 | 4 across top + 4 across bottom
Clips | use invert of sewer manhole average 3000m/200mm apart | x2 | 2 clips
Resin | 1 per manhole | x2 | 1 per manhole
Waterplug | 1 for every 4 manholes | x2 | no waterplug
STORM WATER
| Entry/Exit | Exit AND entry | slot-cutting
Spax screws 75 x 40mm | 1 screw per washer, 2 screws per clip, 2 screws for manhole tage - read formula from BOQ | x2 | as per entry/exit
Clips | use invert of sewer manhole average 3000m/200mm apart | x2 | 2 clips
Waterplug | 1 for every 4 manholes | x2 | no waterplug

## FIBRE BUDGET CALC
GPON Budget Loss Calculations |  |  |  |  | 1550 nm Point to Point Link Attenuation Budget
Splitter Loss |  |  | Calculation |  | Loss/Km | -0.2 | dB/km
Split Ratio | Max Loss (dB) | Typical Loss (dB) | Quantities | Loss Calculations | Loss/Connector (LC/APC) | -0.5 | dB
1:2 | -3.8 | -3.1 |  | 0 | Loss/Splice | -0.1 | dB
1:4 | -7.2 | -6.6 | 1 | -7.2 | Variation Margin | -1 | dB
1:8 | -10.3 | -9.7 |  | 0
1:16 | -13.5 | -12.8 | 1 | -13.5 | Length of the Route | 9740 | meter
1:32 | -16.7 | -16 |  | 0 | Start & Termination Connectors | 2 | Terminations
1:64 | -20.4 | -19.7 |  | 0 | Splice Points (Site-A to Z + Termination) | 8 | Splices
Connector Loss (dB) |  | -0.5 | 2 | -1 | Total Loss/Km | -1.948 | dB/km
Fiber Loss (dB/km) |  | -0.2 | 9740 | -1.948 | Total Connector Loss | -1 | dB
Splice Loss (dB) |  | -0.1 | 8 | -0.8 | Total Splice Loss | -0.8 | dB
Variation Margin (dB) |  | -1 |  | -1 | Variation Margin | -1 | dB
|  |  | Link Loss | -25.448 | TOTAL BUDGET LOSS | -4.748 | dB
Lunch Power |  | 2.5 | Total Loss | -22.948
Note on H9: Splice Points: To be adjusted to actual number of splices of the New/Existing Link.

## AERIAL REQUIREMENTS
Route Start Span or End Span if no Termination Pole |  |  |  | 4 Fibre Poles | 8 Fibre Poles | 12 Fibre Poles | 24 Fibre Poles | 48 Fibre Poles | 72 Fibre Poles | 144 Fibre Poles
Item | Item Code | UOM | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0
Single hook | HB1-10-MI | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thread Bolt with Nut & Washer | M12X220BHT120HD | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deadend | See size chart | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bandit strapping (20M) | BLC136SA | m | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bandit buckle (100 per Box) | BLC956SA | Each | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mid Span Pole |  |  |  | 4 Fibre Poles | 8 Fibre Poles | 12 Fibre Poles | 24 Fibre Poles | 48 Fibre Poles | 72 Fibre Poles | 144 Fibre Poles
Item | Item Code | UOM | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0
Single hook | HB1-10-MI | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thread Bolt with Nut & Washer | M12X220BHT120HD | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tangent | See size chart | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Termination Pole |  |  |  | 4 Fibre Poles | 8 Fibre Poles | 12 Fibre Poles | 24 Fibre Poles | 48 Fibre Poles | 72 Fibre Poles | 144 Fibre Poles
Item | Item Code | UOM | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0
Double hook | HB2-10-MI | Each | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thread Bolt with Nut & Washer | M12X220BHT120HD | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deadend | See size chart | Each | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pole Mounted Optic Fibre Slack Box | PSB300P | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bandit strapping (20M) | BLC136SA | m | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bandit buckle (100 per Box) | BLC956SA | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Directional Change Pole |  |  |  | 4 Fibre Poles | 8 Fibre Poles | 12 Fibre Poles | 24 Fibre Poles | 48 Fibre Poles | 72 Fibre Poles | 144 Fibre Poles
Item | Item Code | UOM | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0
Double hook | HB2-10-MI | Each | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thread Bolt with Nut & Washer | M12X220BHT120HD | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deadend | See size chart | Each | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stays |  |  |  | 4 Fibre Poles | 8 Fibre Poles | 12 Fibre Poles | 24 Fibre Poles | 48 Fibre Poles | 72 Fibre Poles | 144 Fibre Poles
Item | Item Code | UOM | Units | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stay Wire 7 x 1.7mm | STAYWIRE 7/1.70 | m | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stay Guard (Chevron) | FR-ISS 149A | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Guy Grip for 7/1.7mm Stay Wire | TGG 201 | Each | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bracket 45DEG for Stay Wire Grip | TGGB-45 | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Duckbill Stay Anchor | A-88-DB1 | Each | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Item |  |  | Count
Duckbill Stay Anchor |  |  | 0
Stay Guard (Chevron) |  |  | 0
Stay Wire 7 x 1.7mm |  |  | 0
Guy Grip for 7/1.7mm Stay Wire |  |  | 0
Bracket 45DEG for Stay Wire Grip |  |  | 0
Single hook |  |  | 0
Double hook |  |  | 0
M12X220 HDG 120mm Thread Bolt with Nut & Washer |  |  | 0
Dead End FDE 375/414 for ADSS 9.5-10.5mm (12 & 24 Fibre) |  |  | 0
Dead End FDE 415/459 for ADSS 10.54-11.66mm (48 & 72 Fibre) |  |  | 0
Dead end FDE 616/680 for ADSS 15.6-17.27mm (144 Fibre) |  |  | 0
Tangent Support FOT 375/414 for ADSS 9.5-10.5mm (12 & 24 Fibre) |  |  | 0
Tangent Support FOT 398/425 for ADSS 10.1-10.8mm (48 Fibre) |  |  | 0
Tangent Support FOT 426/455 for ADSS 10.8-11.5mm (72 Fibre) |  |  | 0
Tangent Support FOT 595/630 for ADSS 15.11-16.0mm (144 Fibre) |  |  | 0
Pole Mounted Optic Fibre Slack Box |  |  | 0
Bandit strapping (20M) |  |  | 0
Bandit buckle (100 per Box) |  |  | 0

## SPLICE PLAN
INSERT PDF

## ROUTE INFO
TEMP MANHOLE ID | AS BUILD LABEL GENERATOR | BUILD AS BUILD LABEL | POINT OF TERMINATION | MH TYPE | LOCATION | LATITUDE | LONGITUDE | DISTANCE | USE / COMMENTS | TRENCH TYPE | DUCT TYPE | SUB DUCT | CABLE TYPE | SLACK | INVERT | DIAMETER | SPLITTER TYPE | SPLITTER ID
n/a | n/a |  | FIBRE TERMINATION BOX |  |  |  |  | 0 | inside Cabinet | inside Cabinet | inside Cabinet | 14/10-1 WAY | 2 F DUAL DROP CABLE | 5
n/a | n/a | [6 empty] | 2 | inside Cabinet | inside Cabinet | inside Cabinet | 14/10-1 WAY | 2 F DUAL DROP CABLE
n/a | n/a | [6 empty] | 26 | Ceiling | Ceiling | Ceiling | 14/10-1 WAY | 2 F DUAL DROP CABLE
n/a | n/a | [6 empty] | 3 | TRUNKING 25x25 | TRUNKING 25x25 | TRUNKING 25x25 | 14/10-1 WAY | 2 F DUAL DROP CABLE
n/a | n/a | [6 empty] | 6 | 25MM PVC | 25MM PVC | 25MM PVC | 14/10-1 WAY | 2 F DUAL DROP CABLE
n/a | n/a | [6 empty] | 14 | Trench | PAVING | DIRECT BURIED | 14/10-1 WAY | 2 F DUAL DROP CABLE
CA40DD9E9E | CA40DD9E9E |  |  | LA EXISTING | witkoppen road | -26.0363 | 28.0523 | 8 | Trench | SOIL | DIRECT BURIED | 14/10-1 WAY | 2 F DUAL DROP CABLE | 10
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
n/a | n/a
[7 empty] | TOTAL DISTANCE | 59 | [5 empty] | 15 | 0
FIBRE TERMINATION BOX |  | 1 |  | LA 1000X1000 | 0 |  | EXISTING CABLE | 0 |  | CABLE DISTANCE PIVOT
4F WALL MOUNT DB |  | 0 |  | LA 1000X500 | 0 |  | MF 12 | 0 |  | Row Labels | Sum of DISTANCE | Sum of SLACK | Sum of INVERT
12F WALL MOUNT DB |  | 0 |  | LA 500X500 | 0 |  | MF 24 | 0 |  | 2 F DUAL DROP CABLE | 59 | 15
24F WALL MOUNT DB |  | 0 |  | LA DRAWBOX | 0 |  | MF 48 | 0 |  | Grand Total | 59 | 15
48F WALL MOUNT DB |  | 0 |  | LA 400X400 | 0 |  | MF 72 | 0
96F WALL MOUNT DB |  | 0 |  | LA 400X600 | 0 |  | MF 96 | 0
12F PATCH PANEL |  | 0 |  | LA 600X600 (DMC) | 0 |  | MF 144 | 0
24F PATCH PANEL |  | 0 |  | LA 900X900 (DMC) | 0 |  | MF 288 | 0
48F PATCH PANEL |  | 0 |  | New Pole 7,2m (Route Start) | 0 |  | AC 4 (Drop Cable) | 0
72F PATCH PANEL |  | 0 |  | New Pole 9m (Route Start) | 0 |  | AC 8 (Drop Cable) | 0
96F PATCH PANEL |  | 0 |  | New Pole 7,2m (Mid Span) | 0 |  | AC 12 | 0
144F PATCH PANEL |  | 0 |  | New Pole 9m (Mid Span) | 0 |  | AC 24 | 0
288F PATCH PANEL |  | 0 |  | New Pole 7,2m (Direction Change) | 0 |  | AC 48 | 0
NEW 209 JOINT |  | 0 |  | New Pole 9m (Direction Change) | 0 |  | AC 72 | 0
NEW 204 JOINT |  | 0 |  | New Pole 7,2m (Termination) | 0 |  | AC 144 | 0
NEW MINI JOINT |  | 0 |  | New Pole 9m (Termination) | 0 |  | CST 144 | 0
NEW VERTICASA JOINT |  | 0 |  | Existing Pole (Route Start) | 0 |  | CST 288 | 0
EXISTING 209 JOINT |  | 0 |  | Existing Pole (Mid Span) | 0 |  | FOCUS 72 | 0
EXISTING 204 JOINT |  | 0 |  | Existing Pole (Direction Change) | 0 |  | FOCUS 144 | 0 |  | SUB DUCT PIVOT |  |  | DUCT PIVOT
EXISTING MINI JOINT |  | 0 |  | Existing Pole (Termination) | 0 |  | FOCUS 288 | 0 |  | Row Labels | Sum of DISTANCE |  | Row Labels | Sum of DISTANCE
STREET DISTRIBUTION BOX |  | 0 |  | LA EXISTING | 1 |  | VERTICASA (2X12) 24F | 0 |  | 14/10-1 WAY | 59 |  | inside Cabinet | 2
|  |  |  | SEWER | 0 |  | VERTICASA (2X24) 48F | 0 |  | Grand Total | 59 |  | Ceiling | 26
|  |  |  | STORMWATER | 0 |  | VERTICASA (2X48) 96F | 0 |  |  |  |  | TRUNKING 25x25 | 3
|  |  |  | METROCONNECT | 0 |  | 2 F DUAL DROP CABLE | 74 |  |  |  |  | 25MM PVC | 6
|  |  |  | LA 350X350 TOBY BOX | 0 |  | 4 F DUAL DROP CABLE | 0 |  |  |  |  | DIRECT BURIED | 22
|  |  |  | LA 250x230x300 TOBY BOX | 0 |  | 6 F DUAL DROP CABLE | 0 |  |  |  |  | Grand Total | 59
|  |  |  | SERVICE MH | 0 |  | 8 F DUAL DROP CABLE | 0
[7 empty] | 12 F DUAL DROP CABLE | 0
[7 empty] | 24 F DUAL DROP CABLE | 0
|  |  |  | SEWER ENTRY/EXIT | 0 |  | Drop Cable Total | 74 |  | WALL BOX CABLE PIVOT
|  |  |  | SEWER ENTRY&EXIT | 0 |  | 10M WALL BOX CABLE | 0 |  | Row Labels | Count of CABLE TYPE
|  |  |  | SEWER STRAIGHT | 0 |  | 30M WALL BOX CABLE | 0 |  | (blank)
|  |  |  | STORMWATER ENTRY/EXIT | 0 |  | 70M WALL BOX CABLE | 0 |  | Grand Total
|  |  |  | STORMWATER ENTRY&EXIT | 0 |  | 100M WALL BOX CABLE | 0
|  |  |  | STORMWATER SLOT | 0 |  |  | 0
[7 empty] | EXISTING DUCTING | 0
|  |  |  | DIRECT BURIED | 22 |  | 14/10-1 WAY | 61.95
|  |  |  | AERIAL | 0 |  | 14/10-2 WAY | 0
|  |  |  | 40MM AGGRI | 0 |  | 14/10-4 WAY | 0
|  |  |  | 50MM AGGRI | 0 |  | 14/10-7 WAY | 0
|  |  |  | 110MM HDPE PIPE | 0 |  | 12/10-2 WAY | 0 |  | TRENCH PIVOT |  |  | POLE TYPE PIVOT
|  |  |  | 110MM DRILL PIPE | 0 |  | 12/10-4 WAY | 0 |  | Row Labels | Sum of DISTANCE |  | Row Labels | Sum of SLACK
|  |  |  | 50MM BOSAL | 0 |  | 12/10-7 WAY | 0 |  | inside Cabinet | 2 |  | (blank) | 5
|  |  |  | EXISTING DUCT | 0 |  | DIRECT | 0 |  | Ceiling | 26 |  | LA EXISTING | 10
|  |  |  | 25MM SPRAGUE | 0 |  | AERIAL | 0 |  | TRUNKING 25x25 | 3 |  | Grand Total | 15
|  |  |  | 50MM SPRAGUE | 0 |  |  |  |  | 25MM PVC | 6
|  |  |  | 25MM PVC | 6 |  |  |  |  | PAVING | 14
|  |  |  | 50MM PVC | 0 |  | IN BUILDING | 0 |  | SOIL | 8
|  |  |  | TRUNKING 16x16 | 0 |  | SOIL | 8 |  | Grand Total | 59
|  |  |  | TRUNKING 25x25 | 3 |  | AERIAL | 0
|  |  |  | TRUNKING 40x40 | 0 |  | DW PAVING | 0
|  |  |  | EXISTING TRUNKING | 0 |  | DW ASPHALT | 0
|  |  |  | EXISTING CABLE TRAY | 0 |  | RC DRILL | 0
|  |  |  | CABLE TRAY | 0 |  | DW DRILL | 0
|  |  |  | SEWER | 0 |  | TAR CUT | 0
|  |  |  | STORMWATER | 0 |  | PAVING | 14
|  |  |  | 3RD PARTY DUCT | 0 |  | LANDSCAPE | 0
[7 empty] | CONCRETE | 0

## OSP-ISP PLAN
INSERT PDF

## WAYLEAVE APPROVAL
INSERT WL DOC

## PRE-CCTV MAP
INSERT MAP

## CIVIL SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | QTY CIVIL | Total (OSP) | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 1 | 850 | 0 | 1 | 850 | 0 | 0 | 1 | 850 | 0 | 0 | 1 | 850 | 0 | 0 | 1 | 850 | 0 | 0 | 0 | 0
| 2 | TRENCHING
| 2.01 | Excavation of trial pit (400mm width x 1000mm length x 1200mm depth) | m | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.02 | Excavation of drill pit (1500mm width x 1500mm length x 1500mm depth) | m | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.03 | Excavation of trial pit to prove municipal duct (400mm width x 1000mm Length x 700mm depth) | m | 60.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.04 | Excavation of trial pit to prove municipal duct (400mm width x 1000mm Length x 1000mm depth) | m | 86.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.05 | ISP - Excavation and backfilling of trench in normal soil Pickable (300 mm width x 1000 mm depth) | m | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.06 | ISP - Excavation and backfilling of trench in normal soil Pickable (300 mm width x 400 mm depth) (For access layer / FTTH layer in MDU's) | m | 34.65 | 22 | 762.3 | 0 | 22 | 762.3 | 0 | 0 | 22 | 762.3 | 0 | 0 | 22 | 762.3 | 0 | 0 | 22 | 762.3 | 0 | 0 | 0 | 0
| 2.07 | ISP - Excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 81.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.08 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 31.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.09 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 84.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.1 | ISP - Excavation and backfilling of trench in normal soil - 300mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 121.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.11 | ISP - Excavation and backfilling of trench in normal soil - 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 260.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.12 | ISP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 400mm depth) | m | 256.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.13 | ISP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (450mm width x 1000mm depth) | m | 963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.14 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 400mm depth) | m | 31.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.15 | ISP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping 450mm width x 1000mm depth | m | 143.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.16 | ISP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping 300mm width x 400mm depth (For access layer / FTTH layer in MDU's) | m | 34.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.17 | OSP - Excavation and Backfilling of trench in normal soil Pickable (300 mm width x 700 mm depth) | m | 60.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.18 | OSP - Excavation and Backfilling of trench in normal soil Pickable (450 mm width x 1000 mm depth) | m | 129.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.19 | OSP - Applicable to RET Contractors only _ P&Gs: OSP - an additional R5.00 per meter when excavation and backfilling of trench in normal soil pickable (400 mm width x 700 mm depth) | m | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.2 | OSP - Excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) (For access layer/FTTH layer in estates or complexes) | m | 81.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.21 | OSP - Excavation and backfilling of trench in normal soil - 300mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 121.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.22 | OSP - Excavation and backfilling of trench in normal soil - 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 260.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.23 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 70.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.24 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 132.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.25 | OSP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 800mm depth) | m | 273.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.26 | OSP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (450mm width x 1000mm depth) | m | 513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.27 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 84.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.28 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 450mm width x 1000mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 158.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.29 | OSP - Break, excavation and backfilling of trench in hard soil (Mechanical tools required) (450mm width x 1000mm depth) | m | 158.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.3 | OSP - Break, excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping in hard soil (Mechanical tools required) (450mm width x 1000mm depth) | m | 161.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.31 | OSP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping (300mm width x 700mm depth ) | m | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.32 | OSP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping (450mm width x 1000mm depth) | m | 143.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.33 | OSP - Excavation and Backfilling of trench in normal soil Pickable using a Tractor Loader Backhoe (TLB) (300mm width x 600 to 800mm depth) | m | 34.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.34 | OSP - Excavation and Backfilling of trench in Intermediate soil using a Tractor Loader Backhoe (TLB) (300mm width x 600 to 800mm depth) | m | 50.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.35 | OSP - Excavation and Backfilling of trench using a Compact Mechanical Trenching Machine (160mm width x 600 to 800mm depth) | m | 24.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.36 | OSP - Excavation and Backfilling of trench using a Compact Mechanical Trenching Machine including installation of duct in trench (160mm width x 600 to 800mm depth) | m | 30.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.37 | OSP - Excavation and Backfilling of trench in Intermediate soil using a Compact Mechanical Trenching Machine including installation of duct in trench (160mm width x 600 to 800mm depth) | m | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.38 | Excavation of hard rock in trench | m³ | 867.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.39 | Excavation of intermediate rock in trench | m³ | 494.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 | Excavation and backfilling of trench in Hard Soil (400mm width x 700mm depth) | m | 88.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | WALLS & SPECILISED SURFACES
| 2.39 | Build single brick retaining wall | m² | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.4 | Build double brick retaining wall | m² | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.41 | Supply and install interlocking block retaining wall | ea | 26.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.42 | Removal of paving /m2 (Brick paving Slabbed paving and Slasto) | m² | 28.5 | 7 | 199.5 | 0 | 7 | 199.5 | 0 | 0 | 7 | 199.5 | 0 | 0 | 7 | 199.5 | 0 | 0 | 7 | 199.5 | 0 | 0 | 0 | 0
| 2.43 | Supply and install concrete slab for duct protection (300mmx700mmx50mm or as otherwise specified) | ea | 30.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.44 | Supply and place city duct markers including painting with yellow road marking paint | ea | 19.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.45 | DCP testing every 20m | ea | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | PIPES AND DUCTS
| 3.01 | Install 1 x 110mm HDPE pipe in open trench | m | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.02 | Install 1 x 50mm/40mm Aggri pipe in open trench | m | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.03 | Install 2 x 110mm HDPE pipe in open trench | m | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.04 | Supply and install 110mm steel pipe in open trench | m | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.05 | Install 1/2/4/7 way 12/10 micro-duct in existing duct (110mm duct/Bosal/PVC) | m | 7.5 | 9 | 67.5 | 0 | 9 | 67.5 | 0 | 0 | 9 | 67.5 | 0 | 0 | 9 | 67.5 | 0 | 0 | 9 | 67.5 | 0 | 0 | 0 | 0
| 3.06 | Install 1/2/4/7 way 12/10 micro-duct in open trench | m | 3.64 | 22 | 80.08 | 0 | 22 | 80.08 | 0 | 0 | 22 | 80.08 | 0 | 0 | 22 | 80.08 | 0 | 0 | 22 | 80.08 | 0 | 0 | 0 | 0
| 4 | BEDDING PADDING AND BACKFILLING
| 4.01 | Supply and install bedding and padding | m | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.02 | Supply and install of import backfilling material | m³ | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.03 | Stabilizing backfilling material with cement (G2 Mix) | m³ | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.04 | Concrete encasement of pipes (labour and 20 mpa concrete) 300mm width x 220mm depth | m | 122.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.05 | Supply and install cast concrete slab for duct protection 300mm width x 100mm depth | m | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.06 | Concrete encasement of pipes (labour and 20 mpa concrete) 100mm width x 100mm depth | m | 24.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | SURFACE RE-INSTATEMENTS
| 5,01,1 | ISP Trenching Capping | m | 36.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | MANHOLES
| 6.01 | Supply and install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 2287.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.02 | Install large concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x1000mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1452.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.03 | Install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1187.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6,03,1 | Reposition or Install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1187.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.04 | Supply and install large concrete precast manhole including rings with knockouts and precast cover (Internal diameter 1000mm x 1000mm depth wall thickness 65mm to 75mm) | ea | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.05 | Install precast concrete flatpack manhole (605mm x 545mm x 700 mm) | ea | 545.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.06 | Construct single skin clay brick and mortar manhole including cover slab (600mm length x 600mm width x 600mm depth - inside dimensions) | ea | 1383.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.07 | Construct double skin clay brick and mortar manhole including frame and cover (1000mm length x 1000mm width x 1000mm depth - inside dimensions) | ea | 4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.08 | Install Polymer 500x500mm Manhole | ea | 545.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6,08,1 | Reposition or Install Polymer 500x500mm Manhole | ea | 545.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.09 | Install 350mm x350mm Toby box | ea | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.1 | Install 250x230x300mm Toby Box | ea | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.11 | Install Smartlock 400x400mm Manhole | ea | 123.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.12 | Install Smartlock 400x600mm Manhole | ea | 164.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.13 | Install Medium Duty 600x600mm Manhole (DMC) | ea | 504.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.14 | Install Medium Duty 900x900mm Manhole (DMC) | ea | 599.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.15 | Supply and Install Replacement 3rd Party Manhole concrete lid (490-560mm Light duty lid) | ea | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.16 | Supply and Install Replacement 3rd Party Manhole coping and concrete lid (860mm Ø x 75mm depth with 490 mm hole and 560mm light duty lid) | ea | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.17 | Supply and Install Cabinet Plinth - LA Spec1, 2.45m x1.76m x 0.23m | ea | 4899.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.18 | Supply and Install Cabinet Plinth - LA Spec2, 1500x950x100, Install Cabinet Base & Cabinet | ea | 2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.19 | Install LA 23U cabinet on Existing Plinth | ea | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.2 | Supply and install of 3 phase lockable meter box and electrical cabling | ea | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.21 | Install iMonnit Equipment in Indoor POP | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.22 | Install iMonnit Equipment in Street Cabinet POP | ea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | IN-BUILDING INSTALLATION
| 8.01 | External wall core drilling - diameter 50mm - 130mm (Building outer wall ≤250mm wide) | ea | 200 | 1 | 200 | 0 | 1 | 200 | 0 | 0 | 1 | 200 | 0 | 0 | 1 | 200 | 0 | 0 | 1 | 200 | 0 | 0 | 0 | 0
| 8.02 | External wall core drilling - diameter >150mm (Building outer wall > 250mm wide) | ea | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.03 | Core drilling (Concrete apron 300mm deep x 75mm diameter) | ea | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.04 | Supply and install 25mm PVC duct against building/Trunking | m | 16.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.05 | Supply and install 25mm Galvanised Bosal Pipe duct against building | m | 27.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.06 | Supply and install 50mm galvanised bosal against building (2 storey high) | m | 82.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.07 | Supply and Install 50mm galvanised bosal against building (exceeding 2 storey high) | m | 102.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.08 | Supply and Install 90° Bosal Bend | ea | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.09 | Supply and Install Coupling 50mm Bosal | ea | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.1 | Supply and install 50mm pvc pipe (2 storey high) | m | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.11 | Supply and install 50mm pvc pipe (exceeding 2 storey high) | m | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.12 | Supply and install 75mm x 50mm galvanised trunking against building (2 storey high) | m | 61.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.13 | Supply and install 75mm x 50mm galvanised trunking against building (exceeding 2 storey high) | m | 86.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.14 | Supply paint and Preparation and painting of PVC duct/square trunking/bosal | m | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.15 | Supply and install cable trays (RF HD 225mm) | m | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.16 | Supply and install cable trays (Wire Basket 100mm Wide 75mm Depth) including bends and splices | m | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.17 | Supply and install welded wired mesh cable tray (WWHD 100mm) including joiner set | m | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.18 | Supply and install welded wired mesh cable tray (WWHD 200mm) including joiner set | m | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.19 | Install optic cable onto cable trays, risers or in ceilings | m | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.2 | Install 40mm, 7 way, 4 way, 2 way or 1 way duct onto cable tray, riser, in ceiling or under false floor | m | 6.5 | 28 | 182 | 0 | 28 | 182 | 0 | 0 | 28 | 182 | 0 | 0 | 28 | 182 | 0 | 0 | 28 | 182 | 0 | 0 | 0 | 0
| 8.21 | Install PVC duct / sprague / square trunking / bosal against wall, building etc including the drilling of walls | m | 16.39 | 9 | 147.51 | 0 | 9 | 147.51 | 0 | 0 | 9 | 147.51 | 0 | 0 | 9 | 147.51 | 0 | 0 | 9 | 147.51 | 0 | 0 | 0 | 0
| 8.22 | Install PVC duct / against wall, building etc including drills (single drill per anchor point every 1m) _ HV-MDU Application | m | 12.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.23 | ISP - Cut and seal gland plate | ea | 50.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.24 | Install - Slack Box/Junction Box/Home Pass Point MPEbox(J1) | ea | 67.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.25 | ISP - Supply and install fibre glass draw/junction box | ea | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.26 | ISP - Supply and install concrete entry block | ea | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.27 | ISP - Supply and install flex pipe and gland onto bosal and gland plate. (Located where feeders enter BTS site) | ea | 122.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.28 | Install 50mm Stainless Steel Pipe | m | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.29 | Supply and Install 6U x 400+200mm -19" Wall mount Swing Cabinet | ea | 1953.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.3 | Supply and Install 9U x 400+200mm -19" Wall mount Swing Cabinet | ea | 2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.31 | Install up to 12 U Cabinet | ea | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.32 | Prepare and install Fibre Termination Point 4 / 12 / 24 way Wall Mount Distribution Box including accessories | ea | 67.07 | 1 | 67.07 | 0 | 1 | 67.07 | 0 | 0 | 1 | 67.07 | 0 | 0 | 1 | 67.07 | 0 | 0 | 1 | 67.07 | 0 | 0 | 0 | 0
| 8.33 | Supply and Label ODF and Cables on ISP Installations | ea | 90.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.34 | Supply and Label Micro Duct on ISP Installations (Heat Shrink, Arrow Label holders, Brother Tape & Cable Ties) | ea | 90.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.35 | Supply and Label Micro Duct on ISP Installations (Brother Tape on the 1 Way) | ea | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | CABLE FLOATING AND HAULING
| 9.01 | Install 2 / 4 / 6 / 8 / 12 / 24 Fibre Optic Drop Cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5 | 74 | 333 | 0 | 74 | 333 | 0 | 0 | 74 | 333 | 0 | 0 | 74 | 333 | 0 | 0 | 74 | 333 | 0 | 0 | 0 | 0
| 9.02 | Floating of Focus/CST Optic fibre cable in 40mm HDPE duct | m | 5.5
| 9.03 | Floating of Micro cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5
| 9.04 | Pulling of slack between manholes (existing cables Measurement of slack in manhole only) | m | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9.05 | Installation and pulling/Hauling of fibre optical cable in EXISTING ducts | m | 9.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9.06 | Installation and pulling/Hauling of fibre optical cable in NEW ducts | m | 9.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9.07 | Recovery of cable from existing ducts and sewer | m | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13 | AERIAL LINE CABLE
| 13.01 | Survey, Dig / Drill and Plant 7.2 m Pole (100mm-125mm) (Hole 350mm Ø x 1200mm deep) | ea | 210.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.02 | Survey, Dig / Drill and Plant 9 m Pole (125mm-150mm) (Hole 350mm Ø x 1500mm deep) | ea | 252.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.03 | Survey Dig Plant and Fit All Sizes Struts Complete To Poles | ea | 159.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.04 | Survey, Drill or Dig and Plant Stays or Stay Plates and Rods As Surveyed 12mm Stay Hole (350mm X 350mm X 1000mm Deep) Including Stay Wire 7 x 1.7mm, Guy Grip,Bracket 45DEG for Stay Wire Grip and Duckbill Stay Anchor | ea | 186.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.05 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead End FDE 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | ea | 71.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.06 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead End FDE 415/459 for ADSS 10.54-11.66mm (48 & 72 Fibre) | ea | 75.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.07 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead end FDE 616/680 for ADSS 15.6-17.27mm (144 Fibre) | ea | 79.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.08 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | ea | 45.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.09 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 398/425 for ADSS 10.1-10.8mm (48 Fibre) | ea | 55.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.1 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 426/455 for ADSS 10.8-11.5mm (72 Fibre) | ea | 65.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.11 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 595/630 for ADSS 15.11-16.0mm (144 Fibre) | ea | 75.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.12 | Erecting Hauling Tensioning of Fibre Optical Cable on Overhead Cable Route (All Sizes) | m | 4.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.13 | Concreting of Poles or Strut | ea | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.14 | Concreting of All size Stays | ea | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.15 | Install Pole Mounted Optic Fibre Slack Box | ea | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14 | FTTH FULL TURNKEY PRICING
| 14.01 | Price1A: R 3100.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) | ea | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.02 | Price1B: R 3100.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) | ea | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.03 | Price2: R 3100.00 per Demand Point – payable for a NAP/Drop Point (Manhole outside the Gated SDU and MDU Property) | ea | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.04 | Price3: R 3100.00 – payable for a NAP/Drop Point outside a business property | ea | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.05 | Price9A: R 2650.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) Civil and Duct works only | ea | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.06 | Price9B: R 2650.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) Civil and Duct works only | ea | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.07 | Price10A: R 450.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) Fibre Works only | ea | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.08 | Price10B: R 450.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) Fibre Works only | ea | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.09 | Price4A: R 1800.00 per DP – payable for a MDU complex | ea | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.1 | Price4B: R 1800.00 per DP – payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14,10,1 | Price4C: R 200.00 per DP – Survey and Planning : payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14,10,2 | Price4D: R 1600.00 per DP – Build Only : payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.11 | Price5: R 2800.00 per DP – payable for a gated SDU complex where trenching is required | ea | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.12 | Price6: R 3000.00 per DP – payable for a complex not P4 or P5 e.g. forms of trench in a townhouse complex | ea | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.13 | Price7: R 900.00 per FTB – payable per MDU Last Drop Completed | ea | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 14.14 | Price8: R 1 500.00 per FTB – payable per SDU Last Drop Completed | ea | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15 | AS-BUILT DOCUMENTATION
| 15.01 | Complete ISP as-built documents | ea | 1000 | 1 | 1000 | 0 | 1 | 1000 | 0 | 0 | 1 | 1000 | 0 | 0 | 1 | 1000 | 0 | 0 | 1 | 1000 | 0 | 0 | 0 | 0
| 15.02 | Complete OSP as-built information | ea | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 15.03 | Complete ISP as-built documents (FTTX) | ea | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16 | ADDITIONAL
| 16.01 | Portable toilet hire | per day | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.02 | Removal of Waste Material | m³ | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.03 | Sand Bags (bag purchase & filling with sand) | ea | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.04 | Clean 3rd party Manhole and correctly manage cable per manhole | ea | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.05 | Safety File | ea | 500 | 1 | 500 | 0 | 1 | 500 | 0 | 0 | 1 | 500 | 0 | 0 | 1 | 500 | 0 | 0 | 1 | 500 | 0 | 0 | 0 | 0
| 16.06 | Bush Cutting | m | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.07 | Company Contribution of 30% of The Local Labour Cost @ R250 per person/day as Requested By Local Councillors | Man/day | 75 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.07.1 | Link Africa Contribution of 30% of The Local CLO Cost @ R500 per person/day as Requested By Local Councillors | Man/day | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.08 | Abseiling | per day | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.09 | Cherry Picker (Quote) | per day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.1 | Full Turnkey Drop Cable installation by Contractor in Connected Building | Per Drop | 9480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total |  | 4388.96 |  |  | 4388.96 |  |  |  | 4388.96 |  |  |  | 4388.96 |  |  |  | 4388.96 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | -4388.96
[7 empty] | VARIATION ORDER % SI 01 |  | 0% |  | VARIATION ORDER % SI 02 |  | 0% |  | VARIATION ORDER % SI 03 |  | 0% |  | VARIATION ORDER % SI 04 |  | 0% |  | AS BUILD vs PO % | -100%
Note on C72: Not to form part of EXE, will be done on VO based on site instruction from PL.
Note on C79: Not to form part of EXE, will be done on VO based on site instruction from PL.

## JETTING SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | JETTING | Total Jetting | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 12 | FOCUS INSTALLATIONS
| 12.01 | Sewer Manhole Wall Core drilling -120mm | ea | 145.35
| 12.02 | Installation and pulling/Hauling of fibre optical cable (FOCUS) | m | 9.37
| 12.03 | Installation of Entry and Exit manifold including clips | ea | 946.8
| 12.04 | Installation of Entry or Exit manifold including clips | ea | 771.01
| 12.05 | Installation of Straight manifold | ea | 682.35
| 12.06 | Repair of Benching or Manhole Floor per manhole | ea | 276
| 12.07 | Storm water Slot Cutting | ea | 425.96
| 12.08 | Installation of Storm Water Entry and Exit | ea | 586.95
| 12.09 | Installation of Storm Water Entry or Exit | ea | 478
| 12.1 | CCTV Survey Pre Installation | m | 14.38
| 12.11 | CCTV Survey Post Installation | m | 11.5
| 12.12 | High Pressure Jetting -Sewer | m | 25.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.13 | High Pressure Jetting-StormWater | m | 51.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.14 | Over pumping ≤300mm pipe pumping distance not exceeding 150m | hour | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.15 | Sewer sand Bagging per manhole | ea | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | 0
[7 empty] | VARIATION ORDER % SI 01 |  | #DIV/0! |  | VARIATION ORDER % SI 02 |  | #DIV/0! |  | VARIATION ORDER % SI 03 |  | #DIV/0! |  | VARIATION ORDER % SI 04 |  | #DIV/0! |  | AS BUILD vs PO % | #DIV/0!

## DRILLING SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | DRILLING | Total | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 7 | SPECIALISED CROSSINGS
| 7.01 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in normal soil (LA supply the Drill pipe and do the scanning) | m | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.02 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in normal soil (SP supply the Drill pipe and do his own scanning) | m | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.03 | Thrust boring/directional drilling and installation of 2 x 110mm HDPE duct Class 6 or higher in normal soil | m | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.04 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in intermediate rock | m | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.05 | Thrust boring/directional drilling and installation of 2 x 110mm HDPE duct Class 6 or higher in intermediate rock | m | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.06 | Supply and install of pipe and accessories for 1-way bridge attachment for bridge crossing | m | 449.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.07 | Scanning For Directional Drilling | m | 77.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7.08 | Soil displacement / Thrust boring and installation of 1 x 50/43mm sub duct Class 6 or higher in normal or intermediate soil | m | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | 0
[7 empty] | VARIATION ORDER % SI 01 |  | #DIV/0! |  | VARIATION ORDER % SI 02 |  | #DIV/0! |  | VARIATION ORDER % SI 03 |  | #DIV/0! |  | VARIATION ORDER % SI 04 |  | #DIV/0! |  | AS BUILD vs PO % | #DIV/0!

## REINSTATEMENT SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | RE-INSTATEMENT | Total | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 5 | SURFACE RE-INSTATEMENTS
| 5.01 | Re-instatement of asphalt and crusher 300mm width ≤ 100mm thick | m | 172.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.02 | Re-instatement of concrete (18Mpa) 300mm width ≤ 100mm thick | m | 94.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.03 | Re-instatement of asphalt ≤ 100mm thick | m² | 318.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.04 | Re-instatement of asphalt or concrete (And crusher) (20 Mpa) 300mm width >100mm thick - ROAD | m | 297.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.05 | Surface re-instatement - tiles paving inter locking brick and Slabbed paving | m² | 95 | 7 | 665 | 0 | 7 | 665 | 0 | 0 | 7 | 665 | 0 | 0 | 7 | 665 | 0 | 0 | 7 | 665 | 0 | 0 | 0 | 0
| 5.06 | Re-instatement of grass | m | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.07 | Re-establishment of vegetation landscaping and seedlings | m | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total |  | 665 |  |  | 665 |  |  |  | 665 |  |  |  | 665 |  |  |  | 665 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | -665
[7 empty] | VARIATION ORDER % SI 01 |  | 0% |  | VARIATION ORDER % SI 02 |  | 0% |  | VARIATION ORDER % SI 03 |  | 0% |  | VARIATION ORDER % SI 04 |  | 0% |  | AS BUILD vs PO % | -100%

## FLOATING SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | FLOATING | Total | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 3 | PIPES AND DUCTS
| 3.07 | DIT (Duct Integrity Testing) per duct length Minimum rate R1000.00 or as per agreement. For ISP Only | ea | 1000 | 1 | 1000 | 0 | 1 | 1000 | 0 | 0 | 1 | 1000 | 0 | 0 | 1 | 1000 | 0 | 0 | 1 | 1000 | 0 | 0 | 0 | 0
| 3.08 | DIT (Duct Integrity Testing) per duct length for entire route. Minimum rate R1000.00 or as per rate per m | ea | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | CABLE FLOATING AND HAULING
| 9.01 | Install 2 / 4 / 6 / 8 / 12 / 24 Fibre Optic Drop Cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5
| 9.02 | Floating of Focus/CST Optic fibre cable in 40mm HDPE duct | m | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9.03 | Floating of Micro cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9.04 | Pulling of slack between manholes (existing cables Measurement of slack in manhole only) | m | 3
| 9.05 | Installation and pulling/Hauling of fibre optical cable in EXISTING ducts | m | 9.98
| 9.06 | Installation and pulling/Hauling of fibre optical cable in NEW ducts | m | 9.71
| 9.07 | Recovery of cable from existing ducts and sewer | m | 3
| 9.08 | Supply and Label ODF and Cables | ea | 90.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | FIBRE TERMINATION (JOINTING / SPLICE OF FIBRE IN MANHOLES OPTIVAL DISTRIBUTION FRAMES AND PATCH PANELS)
| 10.01 | Supply and Label ODF and Cables | ea | 90.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | FIBRE CABLE TEST PER STRAND AND ACCESSORIES
| 11.01 | Pre haul optic fibre cable test (per fibre) | ea | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11.02 | Post haul optic fibre cable test (per fibre) | ea | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11.03 | Relay section test bi-directional OTDR including report | ea | 25
| 11.04 | Relay section test- Bi-directional Power And Light source testing and fibre verification including report | ea | 20
| 11.05 | Call Out fee per hour | ea | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total |  | 1000 |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |  |  |  | 1000 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | -1000
[7 empty] | VARIATION ORDER % SI 01 |  | 0% |  | VARIATION ORDER % SI 02 |  | 0% |  | VARIATION ORDER % SI 03 |  | 0% |  | VARIATION ORDER % SI 04 |  | 0% |  | AS BUILD vs PO % | -100%

## FOCUS SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | FOCUS INSTALLATION | Total | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 12 | FOCUS INSTALLATIONS
| 12.01 | Sewer Manhole Wall Core drilling -120mm | ea | 145.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.02 | Installation and pulling/Hauling of fibre optical cable (FOCUS) | m | 9.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.03 | Installation of Entry and Exit manifold including clips | ea | 946.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.04 | Installation of Entry or Exit manifold including clips | ea | 771.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.05 | Installation of Straight manifold | ea | 682.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.06 | Repair of Benching or Manhole Floor per manhole | ea | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.07 | Storm water Slot Cutting | ea | 425.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.08 | Installation of Storm Water Entry and Exit | ea | 586.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.09 | Installation of Storm Water Entry or Exit | ea | 478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.1 | CCTV Survey Pre Installation | m | 14.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.11 | CCTV Survey Post Installation | m | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.12 | High Pressure Jetting -Sewer | m | 25.88
| 12.13 | High Pressure Jetting-StormWater | m | 51.75
| 12.14 | Over pumping ≤300mm pipe pumping distance not exceeding 150m | hour | 506
| 12.15 | Sewer sand Bagging per manhole | ea | 23
|  |  |  | Total |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | 0
[7 empty] | VARIATION ORDER % SI 01 |  | #DIV/0! |  | VARIATION ORDER % SI 02 |  | #DIV/0! |  | VARIATION ORDER % SI 03 |  | #DIV/0! |  | VARIATION ORDER % SI 04 |  | #DIV/0! |  | AS BUILD vs PO % | #DIV/0!

## SPLICING SI
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
77G0056723 / 77G0056723
| Project No. / Planning Ref | 77G0056723 / 77G0056723 | ISP SITE ID |  | G1VDA066 |  | BUILD SITE INSTRUCTIONS and AS BUILD QUANTITIES
| Customer Name | VODACOM | Affected Region/s |  | WITKOPPEN RD
| Project Leader | 0 | Planning Date |  | 2023-08-22
| Contractor | INTERNAL OR CONTRACTOR NAME | Link Description (Site A - SiteB) |  | Sunninghill Access POP - BLUE STRIPE T/A CONTRON IT - Car Service City - Sandton
Notes:
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | SPLICING | Total | Site Instruction 01 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 02 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 03 | ACCUMULATED QTY | Total (OSP) | COMMENTS | Site Instruction 04 | ACCUMULATED QTY | Total (OSP) | COMMENTS | AS BUILD QTY (CONTRACTOR) | Total (OSP) | COMMENTS
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0
| 10 | FIBRE TERMINATION (JOINTING / SPLICE OF FIBRE IN MANHOLES OPTIVAL DISTRIBUTION FRAMES AND PATCH PANELS)
| 10.01 | Supply and Label ODF and Cables | ea | 90.91
| 10.02 | Prepare and splice single fibre in existing patch panel joint or ODF (per splice) | ea | 85 | 2 | 170 | 0 | 2 | 170 | 0 | 0 | 2 | 170 | 0 | 0 | 2 | 170 | 0 | 0 | 2 | 170 | 0 | 0 | 0 | 0
| 10.03 | Prepare cable ends and joint for splicing (Loop only) | ea | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10.04 | Prepare and Install Patch Panel/FMT including the preparation of splitters | ea | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | FIBRE CABLE TEST PER STRAND AND ACCESSORIES
| 11.03 | Relay section test bi-directional OTDR including report | ea | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11.04 | Relay section test- Bi-directional Power And Light source testing and fibre verification including report | ea | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total |  | 170 |  |  | 170 |  |  |  | 170 |  |  |  | 170 |  |  |  | 170 |  |  | 0
[7 empty] | VARIATION ORDER AMT SI 01 |  | 0 |  | VARIATION ORDER AMT SI 02 |  | 0 |  | VARIATION ORDER AMT SI 03 |  | 0 |  | VARIATION ORDER AMT SI 04 |  | 0 |  | AS BUILD vs PO | -170
[7 empty] | VARIATION ORDER % SI 01 |  | 0% |  | VARIATION ORDER % SI 02 |  | 0% |  | VARIATION ORDER % SI 03 |  | 0% |  | VARIATION ORDER % SI 04 |  | 0% |  | AS BUILD vs PO % | -100%

## Master BOQ Pricing_2018-01-08 (hidden)
* | To Be viewed in conjunction with BOS_000-MS-BO-010 Rev 5
| CIRCUIT ID | [6 empty] | Domain: | CEO/CFO/CCO/NTM
| Project No. / Planning Ref |  | ISP SITE ID |  |  |  |  | Department: | TECHNICAL
| Customer Name |  | Affected Region/s |  |  |  |  | Document Type: | BILL OF QUANTITIES INFRASTRUCTURE BUILD
| OSP Planner |  | Planning Date |  |  |  |  | Document Name: | LA-TEC-BOQ-001
| ISP Planner | [6 empty] | Revision Number: | 6.13
| Surveyor |  | Link Description (Site A - SiteB) |  |  |  |  | Effective Date: | 2023-02-08
| Notes: | [6 empty] | Date of Next Revision: | 2023-05-01
OSP and ISP BOQ
| NO | ITEM | UNIT | UNIT PRICE | Soil (m³) | Price (m³) | Rate
| 1 | MATERIAL MANAGEMENT
| 1.1 | Collect and delivery of material to Site (>60km) Per Site | Per Site | 850
| 2 | TRENCHING
| 2.01 | Excavation of trial pit (400mm width x 1000mm length x 1200mm depth) | m | 96
| 2.02 | Excavation of drill pit (1500mm width x 1500mm length x 1500mm depth) | m | 185
| 2.03 | Excavation of trial pit to prove municipal duct (400mm width x 1000mm Length x 700mm depth) | m | 60.23 | 0.28 | 215.1071
| 2.04 | Excavation of trial pit to prove municipal duct (400mm width x 1000mm Length x 1000mm depth) | m | 86.04 | 0.4 |  | 86.0429
| 2.05 | ISP - Excavation and backfilling of trench in normal soil Pickable (300 mm width x 1000 mm depth) | m | 68.75
| 2.06 | ISP - Excavation and backfilling of trench in normal soil Pickable (300 mm width x 400 mm depth) (For access layer / FTTH layer in MDU's) | m | 34.65
| 2.07 | ISP - Excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 81.2
| 2.08 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 31.78 | 0.09 |  | 26.4863
| 2.09 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 84.75 | 0.24 | 353.125
| 2.1 | ISP - Excavation and backfilling of trench in normal soil - 300mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 121.36 | 0.21 | 577.9048
| 2.11 | ISP - Excavation and backfilling of trench in normal soil - 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 260.06 | 0.45 |  | 260.0571
| 2.12 | ISP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 400mm depth) | m | 256.8 | 0.12 | 2140
| 2.13 | ISP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (450mm width x 1000mm depth) | m | 963 | 0.45 |  | 963
| 2.14 | ISP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 400mm depth) | m | 31.78 | 0.09 |  | 31.7812
| 2.15 | ISP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping 450mm width x 1000mm depth | m | 143.57 | 0.45 | 319.0444 | 143.5714
| 2.16 | ISP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping 300mm width x 400mm depth (For access layer / FTTH layer in MDU's) | m | 34.2
| 2.17 | OSP - Excavation and Backfilling of trench in normal soil Pickable (300 mm width x 700 mm depth) | m | 60.23 | 0.21 | 286.8095
| 2.18 | OSP - Excavation and Backfilling of trench in normal soil Pickable (450 mm width x 1000 mm depth) | m | 129.06 | 0.45 |  | 129.0643
| 2.19 | OSP - Applicable to RET Contractors only _ P&Gs: OSP - an additional R5.00 per meter when excavation and backfilling of trench in normal soil pickable (400 mm width x 700 mm depth) | m | 5
| 2.2 | OSP - Excavation and backfilling of trench in normal soil - 300mm width x 400mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) (For access layer/FTTH layer in estates or complexes) | m | 81.2
| 2.21 | OSP - Excavation and backfilling of trench in normal soil - 300mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 121.36 | 0.21 | 577.9048
| 2.22 | OSP - Excavation and backfilling of trench in normal soil - 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 260.06 | 0.45 |  | 260.0571
| 2.23 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 70.63 | 0.24 | 294.2917
| 2.24 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 450mm width x 1000mm depth including trench covered by ≤ 100mm of asphalt or concrete (Pickable 18Mpa) | m | 132.43 | 0.45 |  | 132.4313
| 2.25 | OSP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (300mm width x 800mm depth) | m | 273.6 | 0.24 | 1140
| 2.26 | OSP - Excavation and backfilling of trench in normal soil including cutting/asphalt / concrete >100mm thick (450mm width x 1000mm depth) | m | 513 | 0.45 |  | 513
| 2.27 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 400mm width x 700mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 84.75 | 0.24 | 353.125
| 2.28 | OSP - Break (already cut asphalt or concrete), excavation and backfilling of trench in normal soil 450mm width x 1000mm depth including trench covered by >100mm of asphalt or concrete (Pickable 18Mpa) | m | 158.91 | 0.45 |  | 158.9062
| 2.29 | OSP - Break, excavation and backfilling of trench in hard soil (Mechanical tools required) (450mm width x 1000mm depth) | m | 158.91 | 0.45 |  | 158.9062
| 2.3 | OSP - Break, excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping in hard soil (Mechanical tools required) (450mm width x 1000mm depth) | m | 161.95 | 0.45 |  | 161.9528
| 2.31 | OSP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping (300mm width x 700mm depth ) | m | 67 | 0.21 | 319.0476 | 6.77
| 2.32 | OSP - Excavation and backfilling of trench including cutting/breaking of vegetation/ Landscaping (450mm width x 1000mm depth) | m | 143.57 | 0.45 |  | 143.5714
| 2.33 | OSP - Excavation and Backfilling of trench in normal soil Pickable using a Tractor Loader Backhoe (TLB) (300mm width x 600 to 800mm depth) | m | 34.13
| 2.34 | OSP - Excavation and Backfilling of trench in Intermediate soil using a Tractor Loader Backhoe (TLB) (300mm width x 600 to 800mm depth) | m | 50.2
| 2.35 | OSP - Excavation and Backfilling of trench using a Compact Mechanical Trenching Machine (160mm width x 600 to 800mm depth) | m | 24.75
| 2.36 | OSP - Excavation and Backfilling of trench using a Compact Mechanical Trenching Machine including installation of duct in trench (160mm width x 600 to 800mm depth) | m | 30.25
| 2.37 | OSP - Excavation and Backfilling of trench in Intermediate soil using a Compact Mechanical Trenching Machine including installation of duct in trench (160mm width x 600 to 800mm depth) | m | 49.5
| 2.38 | Excavation of hard rock in trench | m³ | 867.39
| 2.39 | Excavation of intermediate rock in trench | m³ | 494.09
| 2.4 | Excavation and backfilling of trench in Hard Soil (400mm width x 700mm depth) | m | 88.35 | 0.28 | 315.5357
| 2 | WALLS & SPECILISED SURFACES
| 2.39 | Build single brick retaining wall | m² | 350
| 2.4 | Build double brick retaining wall | m² | 700
| 2.41 | Supply and install interlocking block retaining wall | ea | 26.26
| 2.42 | Removal of paving /m2 (Brick paving Slabbed paving and Slasto) | m² | 28.5
| 2.43 | Supply and install concrete slab for duct protection (300mmx700mmx50mm or as otherwise specified) | ea | 30.45
| 2.44 | Supply and place city duct markers including painting with yellow road marking paint | ea | 19.65
| 2.45 | DCP testing every 20m | ea | 10
| 3 | PIPES AND DUCTS
| 3.01 | Install 1 x 110mm HDPE pipe in open trench | m | 3
| 3.02 | Install 1 x 50mm/40mm Aggri pipe in open trench | m | 3
| 3.03 | Install 2 x 110mm HDPE pipe in open trench | m | 6
| 3.04 | Supply and install 110mm steel pipe in open trench | m | 130
| 3.05 | Install 1/2/4/7 way 12/10 micro-duct in existing duct (110mm duct/Bosal/PVC) | m | 7.5
| 3.06 | Install 1/2/4/7 way 12/10 micro-duct in open trench | m | 3.64
| 3.07 | DIT (Duct Integrity Testing) per duct length Minimum rate R1000.00 or as per agreement. For ISP Only | ea | 1000
| 3.08 | DIT (Duct Integrity Testing) per duct length for entire route. Minimum rate R1000.00 or as per rate per m | ea | 0.65
| 4 | BEDDING PADDING AND BACKFILLING
| 4.01 | Supply and install bedding and padding | m | 8
| 4.02 | Supply and install of import backfilling material | m³ | 264
| 4.03 | Stabilizing backfilling material with cement (G2 Mix) | m³ | 180
| 4.04 | Concrete encasement of pipes (labour and 20 mpa concrete) 300mm width x 220mm depth | m | 122.95
| 4.05 | Supply and install cast concrete slab for duct protection 300mm width x 100mm depth | m | 70
| 4.06 | Concrete encasement of pipes (labour and 20 mpa concrete) 100mm width x 100mm depth | m | 24.18
| 5 | SURFACE RE-INSTATEMENTS
| 5.01 | Re-instatement of asphalt and crusher 300mm width ≤ 100mm thick | m | 172.97
| 5,01,1 | ISP Trenching Capping | m | 36.89
| 5.02 | Re-instatement of concrete (18Mpa) 300mm width ≤ 100mm thick | m | 94.76
| 5.03 | Re-instatement of asphalt ≤ 100mm thick | m² | 318.72 | 318.72
| 5.04 | Re-instatement of asphalt or concrete (And crusher) (20 Mpa) 300mm width >100mm thick - ROAD | m | 297.5
| 5.05 | Surface re-instatement - tiles paving inter locking brick and Slabbed paving | m² | 95
| 5.06 | Re-instatement of grass | m | 20
| 5.07 | Re-establishment of vegetation landscaping and seedlings | m | 48
| 6 | MANHOLES
| 6.01 | Supply and install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 2287.7
| 6.02 | Install large concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x1000mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1452.57
| 6.03 | Install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1187.7
| 6,03,1 | Reposition or Install small concrete precast manhole including rings with knockouts and precast cover (Internal dimensions 1000mm (diameter)x500mm (Depth) with knockouts wall thickness 65mm to 75mm) | ea | 1187.7
| 6.04 | Supply and install large concrete precast manhole including rings with knockouts and precast cover (Internal diameter 1000mm x 1000mm depth wall thickness 65mm to 75mm) | ea | 3120
| 6.05 | Install precast concrete flatpack manhole (605mm x 545mm x 700 mm) | ea | 545.45
| 6.06 | Construct single skin clay brick and mortar manhole including cover slab (600mm length x 600mm width x 600mm depth - inside dimensions) | ea | 1383.32
| 6.07 | Construct double skin clay brick and mortar manhole including frame and cover (1000mm length x 1000mm width x 1000mm depth - inside dimensions) | ea | 4286
| 6.08 | Install Polymer 500x500mm Manhole | ea | 545.45
| 6,08,1 | Reposition or Install Polymer 500x500mm Manhole | ea | 545.45
| 6.09 | Install 350mm x350mm Toby box | ea | 160
| 6.1 | Install 250x230x300mm Toby Box | ea | 160
| 6.11 | Install Smartlock 400x400mm Manhole | ea | 123.43
| 6.12 | Install Smartlock 400x600mm Manhole | ea | 164.75
| 6.13 | Install Medium Duty 600x600mm Manhole (DMC) | ea | 504.69
| 6.14 | Install Medium Duty 900x900mm Manhole (DMC) | ea | 599.12
| 6.15 | Supply and Install Replacement 3rd Party Manhole concrete lid (490-560mm Light duty lid) | ea | 255
| 6.16 | Supply and Install Replacement 3rd Party Manhole coping and concrete lid (860mm Ø x 75mm depth with 490 mm hole and 560mm light duty lid) | ea | 520
| 6.17 | Supply and Install Cabinet Plinth - LA Spec1, 2.45m x1.76m x 0.23m | ea | 4899.96
| 6.18 | Supply and Install Cabinet Plinth - LA Spec2, 1500x950x100, Install Cabinet Base & Cabinet | ea | 2869
| 6.19 | Install LA 23U cabinet on Existing Plinth | ea | 750
| 6.2 | Supply and install of 3 phase lockable meter box and electrical cabling | ea | 5250
| 6.21 | Install iMonnit Equipment in Indoor POP | ea
| 6.22 | Install iMonnit Equipment in Street Cabinet POP | ea
| 7 | SPECIALISED CROSSINGS
| 7.01 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in normal soil (LA supply the Drill pipe and do the scanning) | m | 250
| 7.02 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in normal soil (SP supply the Drill pipe and do his own scanning) | m | 500
| 7.03 | Thrust boring/directional drilling and installation of 2 x 110mm HDPE duct Class 6 or higher in normal soil | m | 900
| 7.04 | Thrust boring/directional drilling and installation of 1 x 110mm HDPE duct Class 6 or higher in intermediate rock | m | 730
| 7.05 | Thrust boring/directional drilling and installation of 2 x 110mm HDPE duct Class 6 or higher in intermediate rock | m | 1200
| 7.06 | Supply and install of pipe and accessories for 1-way bridge attachment for bridge crossing | m | 449.2
| 7.07 | Scanning For Directional Drilling | m | 77.5
| 7.08 | Soil displacement / Thrust boring and installation of 1 x 50/43mm sub duct Class 6 or higher in normal or intermediate soil | m | 72
| 8 | IN-BUILDING INSTALLATION
| 8.01 | External wall core drilling - diameter 50mm - 130mm (Building outer wall ≤250mm wide) | ea | 200
| 8.02 | External wall core drilling - diameter >150mm (Building outer wall > 250mm wide) | ea | 480
| 8.03 | Core drilling (Concrete apron 300mm deep x 75mm diameter) | ea | 450
| 8.04 | Supply and install 25mm PVC duct against building/Trunking | m | 16.39
| 8.05 | Supply and install 25mm Galvanised Bosal Pipe duct against building | m | 27.79
| 8.06 | Supply and install 50mm galvanised bosal against building (2 storey high) | m | 82.3
| 8.07 | Supply and Install 50mm galvanised bosal against building (exceeding 2 storey high) | m | 102.47
| 8.08 | Supply and Install 90° Bosal Bend | ea | 130
| 8.09 | Supply and Install Coupling 50mm Bosal | ea | 50
| 8.1 | Supply and install 50mm pvc pipe (2 storey high) | m | 40
| 8.11 | Supply and install 50mm pvc pipe (exceeding 2 storey high) | m | 60
| 8.12 | Supply and install 75mm x 50mm galvanised trunking against building (2 storey high) | m | 61.17
| 8.13 | Supply and install 75mm x 50mm galvanised trunking against building (exceeding 2 storey high) | m | 86.17
| 8.14 | Supply paint and Preparation and painting of PVC duct/square trunking/bosal | m | 14.5
| 8.15 | Supply and install cable trays (RF HD 225mm) | m | 200
| 8.16 | Supply and install cable trays (Wire Basket 100mm Wide 75mm Depth) including bends and splices | m | 165
| 8.17 | Supply and install welded wired mesh cable tray (WWHD 100mm) including joiner set | m | 205
| 8.18 | Supply and install welded wired mesh cable tray (WWHD 200mm) including joiner set | m | 225
| 8.19 | Install optic cable onto cable trays, risers or in ceilings | m | 6.5
| 8.2 | Install 40mm, 7 way, 4 way, 2 way or 1 way duct onto cable tray, riser, in ceiling or under false floor | m | 6.5
| 8.21 | Install PVC duct / sprague / square trunking / bosal against wall, building etc including the drilling of walls | m | 16.39
| 8.22 | Install PVC duct / against wall, building etc including drills (single drill per anchor point every 1m) _ HV-MDU Application | m | 12.09
| 8.23 | ISP - Cut and seal gland plate | ea | 50.5
| 8.24 | Install - Slack Box/Junction Box/Home Pass Point MPEbox(J1) | ea | 67.07
| 8.25 | ISP - Supply and install fibre glass draw/junction box | ea | 350
| 8.26 | ISP - Supply and install concrete entry block | ea | 250
| 8.27 | ISP - Supply and install flex pipe and gland onto bosal and gland plate. (Located where feeders enter BTS site) | ea | 122.98
| 8.28 | Install 50mm Stainless Steel Pipe | m | 18
| 8.29 | Supply and Install 6U x 400+200mm -19" Wall mount Swing Cabinet | ea | 1953.5
| 8.3 | Supply and Install 9U x 400+200mm -19" Wall mount Swing Cabinet | ea | 2566
| 8.31 | Install up to 12 U Cabinet | ea | 500
| 8.32 | Prepare and install Fibre Termination Point 4 / 12 / 24 way Wall Mount Distribution Box including accessories | ea | 67.07
| 8.33 | Supply and Label ODF and Cables on ISP Installations | ea | 90.91
| 8.34 | Supply and Label Micro Duct on ISP Installations (Heat Shrink, Arrow Label holders, Brother Tape & Cable Ties) | ea | 90.91
| 8.35 | Supply and Label Micro Duct on ISP Installations (Brother Tape on the 1 Way) | ea | 25
| 9 | CABLE FLOATING AND HAULING
| 9.01 | Install 2 / 4 / 6 / 8 / 12 / 24 Fibre Optic Drop Cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5
| 9.02 | Floating of Focus/CST Optic fibre cable in 40mm HDPE duct | m | 5.5
| 9.03 | Floating of Micro cable in 1 / 2 / 4 / 7 way micro duct | m | 4.5
| 9.04 | Pulling of slack between manholes (existing cables Measurement of slack in manhole only) | m | 3
| 9.05 | Installation and pulling/Hauling of fibre optical cable in EXISTING ducts | m | 9.98
| 9.06 | Installation and pulling/Hauling of fibre optical cable in NEW ducts | m | 9.71
| 9.07 | Recovery of cable from existing ducts and sewer | m | 3
| 9.08 | Supply and Label ODF and Cables | ea | 90.91
| 10 | FIBRE TERMINATION (JOINTING / SPLICE OF FIBRE IN MANHOLES OPTIVAL DISTRIBUTION FRAMES AND PATCH PANELS)
| 10.01 | Supply and Label ODF and Cables | ea | 90.91
| 10.02 | Prepare and splice single fibre in existing patch panel joint or ODF (per splice) | ea | 85
| 10.03 | Prepare cable ends and joint for splicing (Loop only) | ea | 400
| 10.04 | Prepare and Install Patch Panel/FMT including the preparation of splitters | ea | 400
| 11 | FIBRE CABLE TEST PER STRAND AND ACCESSORIES
| 11.01 | Pre haul optic fibre cable test (per fibre) | ea | 12
| 11.02 | Post haul optic fibre cable test (per fibre) | ea | 15
| 11.03 | Relay section test bi-directional OTDR including report | ea | 25
| 11.04 | Relay section test- Bi-directional Power And Light source testing and fibre verification including report | ea | 20
| 11.05 | Call Out fee per hour | ea | 350
| 12 | FOCUS INSTALLATIONS
| 12.01 | Sewer Manhole Wall Core drilling -120mm | ea | 145.35
| 12.02 | Installation and pulling/Hauling of fibre optical cable (FOCUS) | m | 9.37
| 12.03 | Installation of Entry and Exit manifold including clips | ea | 946.8
| 12.04 | Installation of Entry or Exit manifold including clips | ea | 771.01
| 12.05 | Installation of Straight manifold | ea | 682.35
| 12.06 | Repair of Benching or Manhole Floor per manhole | ea | 276
| 12.07 | Storm water Slot Cutting | ea | 425.96
| 12.08 | Installation of Storm Water Entry and Exit | ea | 586.95
| 12.09 | Installation of Storm Water Entry or Exit | ea | 478
| 12.1 | CCTV Survey Pre Installation | m | 14.38
| 12.11 | CCTV Survey Post Installation | m | 11.5
| 12.12 | High Pressure Jetting -Sewer | m | 25.88
| 12.13 | High Pressure Jetting-StormWater | m | 51.75
| 12.14 | Over pumping ≤300mm pipe pumping distance not exceeding 150m | hour | 506
| 12.15 | Sewer sand Bagging per manhole | ea | 23
| 13 | AERIAL LINE CABLE |  |  | m³ | Rate
| 13.01 | Survey, Dig / Drill and Plant 7.2 m Pole (100mm-125mm) (Hole 350mm Ø x 1200mm deep) | ea | 210.57 | 1.32 | 159.5227
| 13.02 | Survey, Dig / Drill and Plant 9 m Pole (125mm-150mm) (Hole 350mm Ø x 1500mm deep) | ea | 252.69 | 1.65 | 153.1455
| 13.03 | Survey Dig Plant and Fit All Sizes Struts Complete To Poles | ea | 159.18 | 2.2 | 72.3545
| 13.04 | Survey, Drill or Dig and Plant Stays or Stay Plates and Rods As Surveyed 12mm Stay Hole (350mm X 350mm X 1000mm Deep) Including Stay Wire 7 x 1.7mm, Guy Grip,Bracket 45DEG for Stay Wire Grip and Duckbill Stay Anchor | ea | 186.55
| 13.05 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead End FDE 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | ea | 71.07
| 13.06 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead End FDE 415/459 for ADSS 10.54-11.66mm (48 & 72 Fibre) | ea | 75.07
| 13.07 | Install M12 x 220 Pigtail bolt nut and washer with Double Hook and Dead end FDE 616/680 for ADSS 15.6-17.27mm (144 Fibre) | ea | 79.07
| 13.08 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 375/414 for ADSS 9.5-10.5mm (4, 8, 12 & 24 Fibre) | ea | 45.12
| 13.09 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 398/425 for ADSS 10.1-10.8mm (48 Fibre) | ea | 55.12
| 13.1 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 426/455 for ADSS 10.8-11.5mm (72 Fibre) | ea | 65.12
| 13.11 | Install M12 x 220 Pigtail bolt nut and washer with Single Hook and Tangent Support FOT 595/630 for ADSS 15.11-16.0mm (144 Fibre) | ea | 75.12
| 13.12 | Erecting Hauling Tensioning of Fibre Optical Cable on Overhead Cable Route (All Sizes) | m | 4.57
| 13.13 | Concreting of Poles or Strut | ea | 228
| 13.14 | Concreting of All size Stays | ea | 258
| 13.15 | Install Pole Mounted Optic Fibre Slack Box | ea | 90
13.16
| 14 | FTTH FULL TURNKEY PRICING
| 14.01 | Price1A: R 3100.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) | ea | 3100
| 14.02 | Price1B: R 3100.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) | ea | 3100
| 14.03 | Price2: R 3100.00 per Demand Point – payable for a NAP/Drop Point (Manhole outside the Gated SDU and MDU Property) | ea | 3100
| 14.04 | Price3: R 3100.00 – payable for a NAP/Drop Point outside a business property | ea | 3100
| 14.05 | Price9A: R 2650.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) Civil and Duct works only | ea | 2650
| 14.06 | Price9B: R 2650.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) Civil and Duct works only | ea | 2650
| 14.07 | Price10A: R 450.00 per Demand Point – payable for a NAP/Drop Point - one side of the road was trenched and road crossings were used to connect the units across the road (Non-gated SDU) Fibre Works only | ea | 450
| 14.08 | Price10B: R 450.00 per Demand Point – payable for a NAP/Drop Point - both sides of the road was trenched to connect the units on both sides of the road (Non-gated SDU) Fibre Works only | ea | 450
| 14.09 | Price4A: R 1800.00 per DP – payable for a MDU complex | ea | 1800
| 14.1 | Price4B: R 1800.00 per DP – payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 1800
| 14,10,1 | Price4C: R 200.00 per DP – Survey and Planning : payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 200
| 14,10,2 | Price4D: R 1600.00 per DP – Build Only : payable for a Gated SDU complex with existing ducts or where above ground deployment can be used no trenching required (brown for all units) | ea | 1600
| 14.11 | Price5: R 2800.00 per DP – payable for a gated SDU complex where trenching is required | ea | 2800
| 14.12 | Price6: R 3000.00 per DP – payable for a complex not P4 or P5 e.g. forms of trench in a townhouse complex | ea | 3000
| 14.13 | Price7: R 900.00 per FTB – payable per MDU Last Drop Completed | ea | 900
| 14.14 | Price8: R 1 500.00 per FTB – payable per SDU Last Drop Completed | ea | 1500
| 15 | AS-BUILT DOCUMENTATION
| 15.01 | Complete ISP as-built documents | ea | 1000
| 15.02 | Complete OSP as-built information | ea | 1000
| 15.03 | Complete ISP as-built documents (FTTX) | ea | 250
| 16 | ADDITIONAL
| 16.01 | Portable toilet hire | per day | 130
| 16.02 | Removal of Waste Material | m³ | 150
| 16.03 | Sand Bags (bag purchase & filling with sand) | ea | 20
| 16.04 | Clean 3rd party Manhole and correctly manage cable per manhole | ea | 40
| 16.05 | Safety File | ea | 500
| 16.06 | Bush Cutting | m | 2.8
| 16.07 | Company Contribution of 30% of The Local Labour Cost @ R250 per person/day as Requested By Local Councillors | Man/day | 75
| 16.07.1 | Link Africa Contribution of 30% of The Local CLO Cost @ R500 per person/day as Requested By Local Councillors | Man/day | 150
| 16.08 | Abseiling | per day | 4500
| 16.09 | Cherry Picker (Quote) | per day | 0
| 16.1 | Full Turnkey Drop Cable installation by Contractor in Connected Building | Per Drop | 9480
Note on C75: Not to form part of EXE, will be done on VO based on site instruction from PL.

## Network Types (hidden)
Network Type No. | Network Infrastructure Unique ID | Network Infrastructure Description
| Blank | Blank
1 | NET1 | Link Africa traditional network, including [PoPs, Fibre Routes Link Africa, and Connected Locations]
2 | NET2.1 | Multitenant Building [Partially Reticulated: e.g., Retail/Malls]
3 | NET2.2 | Multitenant Building [Fully Reticulated: e.g., Retail/Malls]
4 | NET3.1 | 3rd Party/Managed Controlled Network Area on LA built network.
5 | NET3.2 | 3rd Party/Managed Controlled Network Area on acquired network.
6 | NET4 | Pre-Fibred FTTB Precinct
7 | NET5 | Network POP on the acquired/LA-Net2 network, with build required to it. [excluding DFA-Precinct node]
8 | NET6.1 | Peregrine - DFA Access/Backhaul Link
| NET6.2.0 | Helios - DFA Access/Backhaul Link
| NET6.2.1 | DD/IS Managed Port Enterprise Service - DFA Access/Backhaul Link
| NET6.3 | Calypte Metro - DFA Access/Backhaul Link
| NET6.4 | Calypte Long Haul - DFA Access/Backhaul Link
| NET6.5 | Magellan - DFA Access/Backhaul Link
| NET6.6 | Tachyon - DFA Access/Backhaul Link
9 | NET7 | SAS Fibre Route
10 | NET8 | 3rd Party Backhaul or Last-Mile Link - e.g., MTN, BBI, Liquid
11 | NET9 | POPs or DC that permit only Internal Clients Sales, no external connections are permitted into this POP